## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Modi Realty Pocharam LLP(NGH)
Site: |  | 2021-05-15
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where where PO/WO not prepared 3 working days after requisition
181574 | 2021-05-07 | Battary vehicle | Estimate to be prepared
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
181567 | 2021-04-26 | Safety shoes | Pick up from global safety
181573 | 2021-05-04 | Bio metric machine | Pick up from supplier
181575 | 2021-05-10 | MS Gate | Pick up from SSLLP
181576 | 2021-05-10 | Pulse oximeter | Puchase locally and cancel this requisition