## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Modi Realty Pocharam LLP(NGH)
Site: |  | 2021-05-08
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where where PO/WO not prepared 3 working days after requisition
181568 | 2021-04-26 | Calmshell card | PO 77279
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
181558 | 2021-03-19 | Visiting cards | Promotions to follow up
181560 | 2021-04-02 | Ms gate | Pick up from ssllp
181567 | 2021-04-26 | Safety shoes | pick up from supplier