## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-05-22
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
180630 | 2021-02-11 | Al sliding windows | Pick up from SSLLP
180722 | 2021-03-20 | Wifi cameras | No stock with supplier
180766 | 2021-04-19 | UPVC Sliding windows | Work under process
180771 | 2021-04-20 | MS L angles | Pick from supplier Dilpreet, global
180786 | 2021-05-10 | Tan brown granite | Pick up from SSLLP
180787 | 2021-05-10 | Grills | Pick up from SSLLP
180788 | 2021-05-11 | Rod cutting blades | Pick up from supplier, shiv shakti