## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-05-22
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163459 | 2021-04-26 | Calmshell cards | PO 77275
163463 | 2021-04-27 | Tube lights | PO 77219
163464 | 2021-04-27 | Safety shoes | PO 77220
163460 | 2021-04-27 | Camera | Send req again
163467 | 2021-04-19 | Foot valve | Searching in market by minish
163465 | 2021-04-28 | Laptop | PO 77042
163471 | 2021-05-01 | Borewell drilling | Remove this requisition it wont have PO
163483 | 2021-05-10 | Pulse ocy meter | Purchase locally
163490 | 2021-05-11 | Tools and spares | Send req again
163491 | 2021-03-15 | Steel | Follow up with minish
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163357 | 2021-02-10 | Autometic passenger lift | Work under process
163405 | 2021-03-16 | Project folders A1&A2 | Pick up from Venkataramana Stationery
163418 | 2021-03-24 | Curb stone | Deliverd
163434 | 2021-03-24 | Mask | Puchase locally not avialable
163442 | 2021-04-17 | Spray paint | Pick up from Ganji Venkanna
163449 | 2021-04-21 | MS Light stand | Deliverd
163472 | 2021-05-01 | Plumbing material | Pick up from ssllp
163479 | 2021-05-06 | Control panel | Pick up from supplier
163482 | 2021-05-08 | Dust bin covers | Pick up from supplier
163486 | 2021-05-10 | MS Stand | Under production