## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-06-05
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing 8mm toughness | Document is Estimation
177482 | 18.03.2021 | Kitchen unit | Quotes to be receive
177483 | 18.03.2021 | Kitchen unit | Quotes to be receive
177484 | 18.03.2021 | Kitchen unit | Quotes to be receive
177485 | 18.03.2021 | Kitchen unit | Quotes to be receive
177486 | 18.03.2021 | Kitchen unit | Quotes to be receive
177492 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177493 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177497 | 19.03.2021 | Grills | Po to be issue
177502 | 19.03.2021 | Sanitary | Rates to be finalized by MD
177503 | 19.03.2021 | Sanitary | Rates to be finalized by MD
177525 | 24.03.2021 | Refrigerator | Po to be issue
177588 | 17.04.2021 | Waterproofing | Document is in estimation
177593 | 21.04.2021 | Grey Stone Macherla | Po to be issue
177603 | 24.04.2021 | Cinder coal Ash | Estimate to be prepare
177630 | 04.05.2021 | Grills | Requisition send to MD sApproval
177646 | 10.05.2021 | Ro plant chemical | Requisition send to MD sApproval
177650 | 13.05.2021 | SS screws | Requisition send to MD sApproval
177651 | 17.05.2021 | Main door beeding | Requisition send to MD sApproval
177660 | 21.05.2021 | Tube light | Requisition send to MD sApproval
177669 | 28.05.2021 | Tube light | Requisition send to MD sApproval
177672 | 28.05.2021 | Sadar Ali Grey Granite | Document is in estimation
177673 | 28.05.2021 | Sadar Ali Grey Granite | Document is in estimation
177674 | 28.05.2021 | Sadar Ali Grey Granite | Document is in estimation
177675 | 28.05.2021 | Sadar Ali Grey Granite | Document is in estimation
177676 | 28.05.2021 | Sadar Ali Grey Granite | Document is in estimation
177677 | 28.05.2021 | Sadar Ali Grey Granite | Document is in estimation
177678 | 28.05.2021 | Janata paste ,Araldite | Requisition send to MD sApproval
177682 | 01.06.2021 | Transformer to 800Amps | Requisition send to MD sApproval
177683 | 01.06.2021 | Copper plate | Requisition send to MD sApproval
177684 | 01.06.2021 | Z angle templates | Requisition send to MD sApproval
177685 | 02.06.2021 | False ceiling | Requisition send to MD sApproval
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177387 | 16.02.2021 | Upvc sliding windows | Work under progress
177404 | 24.02.2021 | Grills 2x2 | NO stock at supplier
177447 | 11.03.2021 | Concrete grigio | No stock at supplier SSLLP
177472 | 17.03.2021 | Down commers, sprinklers | Work under progress
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478&177479 | 17.03.2021 | Pannel doors part 1 | Half of the material we received remaining supplier arrange the material delivered by next week
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177488 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177491 | 18.03.2021 | Grills part 1 | Half of the material we received remaining material supplier arrange the material delivered by next week SSLLP
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177498 | 19.03.2021 | Stainless steel sink | Supplier arrange the material delivered by next week
177513 | 20.03.2021 | Cu multi wires ,tv ,spring wire | Half of the material we received remaining material supplier arrange the material delivered by next week
177541 | 31.03.2021 | Pannel skin doors | Supplier Arrange the Material delivered by next week SSLLP
177543 | 31.03.2021 | Pannel skin doors | Supplier Arrange the Material delivered by next week SSLLP
177544 | 31.03.2021 | Doors beeding | will pick up from SSLLP next week
177559 | 06.04.2021 | Luna ,ultra , Malaysian lt,dk, hl | Half of the material we received remaining material supplier arrange the material delivered by next week
177562 | 06.04.2021 | Vitrified tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177563 | 06.04.2021 | Kitchen dado,utility floor tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177564 | 06.04.2021 | Ms Railing | No stock At supplier
177582 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Half of the material we received remaining material supplier arrange the material delivered by next week
177591 | 20.04.2021 | AMC for Generator Set | Work under progress
177597 | 23.04.2021 | Bath room tiles | Half of the material we received remaining we will pick up from SSLLP next week
177599 | 24.04.2021 | Grigio serena, concrete beige & concrete grigio | Half of the material we received remaining we will pick up from GMR site
177608 | 26.04.2021 | DB 3 phase | No stock at supplier SSLLP
177630 | 04.05.2021 | MS grills | No stock At supplier
177639 | 06.05.2021 | Plasticizer | Half of the material we received remaining we will pick up from SSLLP next week
177642 | 08.05.2021 | Kitchen unit | Supplier Arrange the material delivered by next week
177648 | 12.05.2021 | Roff chemical | Half of the material we received remaining we will pick up from SSLLP next week
177652 | 17.05.2021 | Birla putty | Material is ready we will pick up from SSLLP
177656 | 20.05.2021 | Road blockers | Material is ready we will pick up from SSLLP
177657 | 21.05.2021 | Pvc Pipes | Half of the material we received remaining we will pick up from SSLLP next week
177679 | 31.05.2021 | Engineers jackets | Supplier Arrange the Material delivered by next week