## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-06-06
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163460 | 2021-04-27 | Camera | Online purchase
163467 | 2021-04-19 | Foot valve | Searching in market by minish
163465 | 2021-04-28 | Laptop | To be purchase by system admin
163479 | 2021-05-06 | Control panel floating switch | Online purchase
163483 | 2021-05-10 | Pulse oxymener | Site purchase, remove from this remark
163490 | 2021-05-11 | Tools and spares | Cancelled
163488 | 2021-05-11 | Visiting cards | Promitions to follow up
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163357 | 2021-02-10 | Autometic passenger lift | Work under process
163405 | 2021-03-16 | Project folders A1&A2 | Pick up from Venkataramana Stationery
163418 | 2021-03-24 | Curb stone | Deliverd
163434 | 2021-03-24 | Mask | Puchase locally not avialable at SSLLP
163464 | 2021-07-27 | Safety shoes | Deliverd
163442 | 2021-04-17 | Spray paint | Deliverd
163449 | 2021-04-21 | MS Light stand | Deliverd
163472 | 2021-05-01 | GI Material | Puick up from Praful sanitary
163482 | 2021-05-08 | Dust bin covers | Deliverd
163486 | 2021-05-10 | MS Stand | Under production
163497 | 2021-05-19 | Stationert material | Deliverd
163498 | 2021-05-19 | Road blockers | Pickup from SOVLLP
163503 | 2021-05-21 | Male safety shoes | Deliverd
163504 | 2021-05-31 | CPVC Material | Pick up from Praful sanitary