## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estates
Site: |  | 2021-06-05
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
175250 | 2021-04-10 | Parking benches | Estimate to be prepare
175252 | 2021-04-10 | MS Square pipes | Cancelled
175279 | 2021-05-07 | BT Road patching | Enquiry in market
175285 | 2021-05-13 | Panel doors | PO77815
175283 | 2021-05-13 | Sanitary | PO 77466
175282 | 2021-05-13 | Electrical wires | PO 77464
175281 | 2021-05-11 | Laptop bags | Online purchase
175287 | 2021-05-19 | Boom barrier | PO 77487
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
175243 | 2021-03-20 | Bison board | Pick up from supplier, Vaishnavi agencies
175284 | 2021-05-13 | Lappum bags | Pick up from SSLLP