## Anx - A - Attendance details
Annexure - A - Circular no. 807(b)
Details of labour charges
Name of contractor: |  | Home Line Infra
Company name: |  | Nilgiri Estate
Project name: |  | Nilgiri Estates
Date:
Period |  | From: | 2021-06-03 | To: | 2021-06-10
Sl. No. | Work Type | Worker Type | Quantity | Rate | Amount
1 | Civil work | Mason | 0 | 650 | 0
2 | Civil work | Male helper | 0 | 500 | 0
3 | Civil work | Female helper | 0 | 350 | 0
4 | RCC work | Mason | 0 | 0 | 0
5 | RCC work | Male helper | 0 | 0 | 0
6 | RCC work | Female helper |  | 0 | 0
7 | RCC work | Mason | 0 | 0 | 0
8 | Earth work | Male helper | 0 |  | 0
9 | Earth work | Female helper | 0 | 0 | 0
10 | Electrician | Mason | 0 | 0 | 0
11 | Electrician | Male helper | 0 | 0 | 0
| Total |  |  |  | 0
Payment recommended by project manager:
Payment approved by MD:
| Prepared by: |  | Approved by: |  | MDs approval
Name | Kavitha |  | Akhil
Sign
Date
Note:
1. Attach attendance summary from database
2. Recoomend payment as per our guideline rates for wages.

## Anx - B - Hire charges
Annexure - B - Circular no. 807(b)
Details of hire charges
Name of contractor: |  | Home Line Infra
Company name: |  | Nilgiri Estate
Project name: |  | Nilgiri Estates
Date: |  | 2021-06-11
Period |  | From: | 2021-06-03 | To: | 2021-06-10
Sl. No. | Equipment Type | Quantity | Rate | Units | Amount
1 | JCB |  | 800 | Hrs | 0
2 | Tractor tipper with labour | 0 | 375 | 0 | 0
3 | Tractor tipper without labour | 1 | 1800 | Per day | 1800
4 | Concrete mixer with diesel | 0 | 2000 | Per day | 0
including operator batta
| Total |  |  |  | 1800
Payment recommended by project manager:
Payment approved by MD:
| Prepared by: |  | Approved by: |  | MDs approval
Name | Kavitha |  | Akhil
Sign
Date
Note:
1. Attach hirecharges summary from database
2. Recoomend payment as per our guideline rates for hirecharges.

## Anx - C - Material received
Annexure - C - Circular no. 807(b)
Details of magterial received
Name of contractor: |  | Home Line Infra
Company name: |  | Nilgiri Estate
Project name: |  | Nilgiri Estates
Date: |  | 2021-06-11
Period |  | From: | 2021-06-03 | To: | 2021-06-10
Sl. No. | Material type | Received date | Inward no. | Quantity | Units | Rate | Amount
1 | Robo course sand | 2021-06-08 | 11922 | 600 | cft | 25 | 15000
2 | Robo course sand | 2021-06-08 | 11923 | 589 | cft | 25 | 14725
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
| Total | [5 empty] | 29725
Payment recommended by project manager:
Payment approved by MD:
| Prepared by: |  |  | Approved by: |  | MDs approval
| Kavitha |  |  | Akhil
Name
Sign
Date
Note:
1. Attach inward summary report from database.
2. Attach details sheet from database with photographs
3. Recoomend payment as per our guideline rates for building material.
4. Other material rates can be adopted as per bills produced.

## Anx - D - Milestone report
Annexure - D - Circular no. 807(b)
Mile stone report for CR.
Name of contractor: |  |  |  | HomeLline Infra
Company name: |  |  |  | Nilgiri Estate
Project name: |  |  |  | Nilgiri Estates
Date: |  |  |  | 2021-06-11
S No | Villa no. | Type | SBUP | Work start date | Completion of plinth | Completion of RCC | Completion of brickwork and plastering | Completion of stage I | Completion of stage II | Completion of stage III | Completion of stage IV | Date of physical posession
1 | 80 A | A2 | 1205 | 2016-05-12 | 2017-09-05 | 2018-01-23 | 2018-04-23 | 2018-05-30 | 2018-07-31 | 2018-10-04 | 2019-05-17 | 2019-05-20
2 | 80 B | A2 | 1205 | 2016-12-28 | 14-07-17 | 2017-11-15 | 2018-03-22 | 2018-05-30 | 2018-07-31 | 2018-10-09 | 2019-04-25 | 2019-05-02
3 | 80 C | A1 | 1215 | 2017-06-05 | 2017-07-24 | 2018-01-23 | 2018-03-26 | 2018-05-30 | 2018-07-31 | 2018-10-09 | 2019-11-19 | 2019-11-19
4 | 80 D | A1 | 1215 | 2016-12-12 | 14-07-17 | 2017-11-15 | 2018-03-22 | 2018-05-30 | 2018-08-01 | 2018-10-09 | 2019-05-03 | 2019-05-18
5 | 81 | AA1 | 1175 | 2016-11-14 | 2017-01-16 | 2017-10-05 | 2018-02-17 | 2018-05-30 | 2018-07-04 | 2018-08-02 | 2019-01-16 | 2019-02-02
6 | 82 | AA1 | 1175 | 2016-11-05 | 2017-01-18 | 2017-10-17 | 2018-02-22 | 2018-05-30 | 2018-07-04 | 2018-07-25 | 2020-02-14 | 2020-02-14
7 | 83 | AA1 | 1175 | 2016-11-07 | 2017-01-20 | 28-08-17 | 2018-02-22 | 2018-05-30 | 2018-06-20 | 2018-07-25 | 2019-06-25 | 2019-09-08
8 | 84 | AA1 | 1175 | 2016-11-08 | 2017-03-24 | 24-08-17 | 2018-02-22 | 2018-05-30 | 2018-06-20 | 2018-07-25 | 2019-06-25 | 2019-07-04
9 | 85 | AA1 | 1175 | 2016-12-19 | 2017-03-15 | 2017-10-26 | 2018-02-25 | 2018-05-30 | 2018-07-04 | 2018-08-01 | 2019-02-02 | 2019-02-16
10 | 86 | AA1 | 1175 | 2017-01-20 | 2017-03-15 | 2017-10-26 | 2018-02-25 | 2018-05-30 | 2018-07-04 | 2018-07-18 | 2021-03-11
11 | 87 | AA1 | 1175 | 2016-12-02 | 2017-03-07 | 2017-10-26 | 2018-03-01 | 2018-05-30 | 2018-07-04 | 2018-08-01 | 2019-01-03 | 2019-01-21
12 | 88 | AA1 | 1175 | 2016-12-08 | 2017-02-04 | 2017-10-26 | 2018-03-01 | 2018-05-30 | 2018-07-04 | 2018-08-01 | 2018-12-04 | 2018-12-24
13 | 89 | AA1 | 2170 | 2017-06-15 | 2017-09-18 | 2017-12-09 | 2018-05-30 | 2018-07-03 | 2018-08-28 | 2018-09-19 | 2019-01-27 | 2019-02-10
14 | 90 | AA1 | 1175 | 2017-06-05 | 2017-09-18 | 2017-12-09 | 2018-04-16 | 2018-07-03 | 2018-08-28 | 2018-10-04 | 2019-08-02 | 2019-08-05
15 | 91 | AA1 | 1175 | 2017-01-02 | 2017-01-13 | 2017-05-22 | 2018-03-22 | 2018-05-30 | 2017-12-21 | 2018-10-22 | 2020-02-03 | 2020-02-03
16 | 92 | AA1 | 1175 | 2016-11-10 | 2017-02-04 | 2017-05-22 | 2018-03-22 | 2018-05-30 | 2018-07-06 | 2018-08-27 | 2020-02-19 | 2020-02-19
17 | 93 | AA1 | 1175 | 2016-11-11 | 2017-02-06 | 2017-06-18 | 2018-03-22 | 2018-05-30 | 2018-07-06 | 2018-08-27 | 2019-04-03 | 2019-04-06
18 | 94 | AA1 | 1175 | 2016-12-17 | 2017-02-21 | 2017-05-25 | 2018-03-22 | 2018-05-30 | 2018-07-11 | 2018-09-03 | 2019-04-01 | 2019-04-02
19 | 95 | AA1 | 1175 | 2016-12-14 | 2017-02-21 | 2017-07-15 | 2018-03-22 | 2018-05-30 | 2018-07-11 | 2018-08-29 | 2019-06-12 | 2019-07-05
20 | 96 | AA1 | 1175 | 2017-01-03 | 2017-02-21 | 2017-10-05 | 2018-03-22 | 2018-05-30 | 2018-07-18 | 2018-09-03
21 | 97 | AA1 | 1175 | 2017-01-18 | 2017-03-27 | 2017-06-15 | 2018-04-16 | 2018-06-20 | 2018-08-17 | 2018-10-04
22 | 98 | AA1 | 1175 | 2017-02-10 | 2017-03-27 | 2017-06-20 | 2018-08-14 | 2018-08-27 | 2018-11-22 | 2018-11-24 | 2019-09-01 | 2019-09-05
23 | 99 | AA1 | 1175 | 2016-12-21 | 2017-04-05 | 2017-06-18 | 2018-08-14 | 2018-09-26 | 2018-11-22 | 2018-11-24 | 2019-11-05 | 2019-11-05
24 | 100 | AA2 | 2170 | 2016-11-22 | 2017-02-04 | 2017-09-23 | 2018-07-17 | 2018-11-12 | 2019-02-21 | 2018-09-03 | 2019-05-04 | 2019-05-22
25 | 101 | AA2 | 1175 | 2017-01-19 | 2017-05-04 | 2017-07-13 | 2017-11-04 | 2017-12-12 | 2017-12-21 | 2019-05-27 | 2019-07-22 | 2019-07-24
26 | 102 | AA2 | 1175 | 2017-12-14 | 2018-03-29 | 2018-08-07 | 2019-01-17 | 2019-03-09 | 2019-07-10 | 2019-08-21 | 2020-10-10
27 | 103 | AA2 | 1175 | 2018-02-15 | 2018-05-07 | 2018-08-07 | 2019-01-14 | 2019-01-22 | 2019-03-09 | 2019-04-10 | 2020-11-11
28 | 104 | AA2 | 1175 | 2017-11-14 | 2018-05-07 | 2018-08-07 | 2018-12-19 | 2019-02-11 | 2019-06-08 | 2019-08-21 | 2019-09-26 | 2019-09-26
29 | 105 | AA2 | 1175 | 2018-02-21 | 2018-05-21 | 2018-08-07 | 2018-11-22 | 2019-01-23 | 2019-03-06 | 2019-05-28 | 2020-10-25 | 2020-11-11
30 | 106 | AA2 | 1175 | 2017-12-12 | 2018-05-26 | 2018-08-07 | 2018-10-22 | 2019-01-14 | 2019-03-07 | 2019-05-11 | 2019-09-14 | 2019-09-14
31 | 107 | AA2 | 1175 | 2017-10-18 | 2018-04-11 | 2018-08-07 | 2018-10-17 | 2019-02-16 | 2019-04-04 | 2019-12-18 | 2021-03-10
32 | 108 | AA2 | 1175 | 2017-02-08 | 2018-03-13 | 2018-08-07 | 2019-01-21 | 2019-02-21 | 2019-07-19 | 2019-12-23
33 | 109 | AA2 | 2170 | 2017-06-05 | 2017-09-12 | 2018-03-30 | 2018-07-19 | 2018-10-05 | 2019-01-23 | 2019-05-13
34 | 110 | AA2 | 1175 | 2017-06-20 | 2017-09-22 | 2018-02-14 | 2018-08-14 | 2018-10-06 | 2019-01-20 | 2019-05-13 | 2019-09-26 | 2019-09-26
35 | 111 | AA2 | 1175 | 2017-01-02 | 2017-02-07 | 2017-12-09 | 2018-03-22 | 2018-08-16 | 2018-11-27 | 2018-03-11 | 2019-11-12 | 2019-11-12
36 | 112 | AA2 | 1175 | 2017-01-03 | 2017-03-07 | 2017-12-09 | 2018-03-22 | 2018-08-16 | 2018-12-04 | 2019-02-27 | 2019-09-28 | 2019-09-28
37 | 113 | AA2 | 1175 | 2017-03-03 | 2017-09-21 | 2018-04-02 | 2018-10-11 | 2009-01-05 | 2019-05-21 | 2019-08-21 | 2020-01-09 | 2020-01-09
38 | 114 | AA2 | 2170 | 2017-02-07 | 2018-01-02 | 2018-08-03 | 2018-12-06 | 2019-03-09 | 2019-08-14 | 2019-08-24 | 2019-09-22 | 2019-10-04
39 | 115 | AA2 | 1175 | 2017-01-12 | 2018-01-02 | 2018-06-19 | 2018-12-06 | 2019-02-18 | 2019-05-29 | 2019-08-24 | 2019-11-26 | 2019-11-26
40 | 116 | AA2 | 2170 | 2017-01-13 | 2017-04-04 | 2018-08-03 | 2019-02-21 | 2019-03-26 | 2019-07-09 | 2019-10-16 | 2019-11-23 | 2019-11-23
41 | 117 | AA2 | 1175 | 2017-12-28 | 2018-03-27 | 2018-07-03 | 2018-12-10 | 2019-01-14 | 2019-02-19 | 2019-03-16 | 2019-05-19 | 2019-06-08
42 | 118 | AA2 | 1175 | 2017-03-08 | 2018-03-26 | 2018-07-03 | 2018-11-30 | 2019-02-01 | 2019-05-24 | 2019-10-16 | 2020-03-20
43 | 119 | BB1 | 915 | 2017-02-01 | 2017-04-04 | 2018-03-15 | 2018-11-28 | 2018-12-29 | 2019-07-09 | 2019-10-16
44 | 120 | BB1 | 915 | 2017-02-08 | 2017-04-04 | 2018-03-09 | 2018-10-04 | 2018-12-18 | 2019-06-21 | 2019-08-21
45 | 121 | BB1 | 915 | 2017-02-09 | 2017-04-15 | 2018-02-28 | 2018-07-24 | 2018-12-29 | 2019-03-27 | 2019-10-16 | 2020-02-10 | 2020-02-10
46 | 122 | BB1 | 915 | 2017-03-08 | 2017-09-22 | 2018-02-28 | 2018-06-07 | 2018-12-04 | 2019-03-12 | 2019-04-09 | 2019-10-16 | 2019-10-31
47 | 123 | BB1 | 1695 | 2017-05-25 | 2017-12-14 | 2018-05-28 | 2018-05-26 | 2019-03-01 | 2019-06-28 | 2020-01-13 | 2020-01-08 | 2020-01-08
48 | 124 | BB1 | 915 | 2017-04-04 | 2017-12-14 | 2018-02-28 | 2018-05-30 | 2018-12-22 | 2019-03-07 | 2019-08-24 | 2019-10-14 | 2019-10-14
49 | 125 | BB1 | 915 | 2017-03-08 | 2017-07-07 | 2018-02-07 | 2018-05-30 | 2018-12-14 | 2019-02-23 | 2019-05-03 | 2019-09-30 | 2019-10-16
50 | 126 | BB1 | 915 | 2017-02-08 | 2017-07-07 | 2018-02-07 | 2018-05-30 | 2018-12-14 | 2019-02-15 | 2019-08-21
51 | 127 | BB1 | 915 | 2017-08-03 | 2017-12-15 | 2018-09-28 | 2020-05-27 | 2020-07-30
52 | 128 | BB1 | 915 | 2018-01-10 | 2018-08-11 | 2018-11-09 | 2020-05-20 | 2020-07-30
53 | 129 | BB1 | 915 | 2018-04-25 | 2018-10-11 | 2019-02-21 | 2020-05-27 | 2020-07-30
54 | 130 | BB1 | 915 | 2018-08-08 | 2018-10-12 | 2019-02-21 | 2020-05-30 | 2020-08-24
55 | 131 | BB1 | 915 | 2018-07-04 | 2018-10-24 | 2019-02-27 | 2020-05-30 | 2020-08-24
56 | 132 | BB1 | 915 | 2018-06-14 | 2018-10-30 | 2019-02-27 | 2020-05-30 | 2020-08-24
57 | 133 | BB1 | 915 | 2017-04-06 | 2017-08-18 | 2018-01-23 | 2019-03-07 | 2019-04-09 | 2019-09-16 | 2019-10-18 | 2019-11-26 | 2019-12-15
58 | 134 | BB1 | 915 | 2017-02-18 | 2017-08-18 | 2018-01-12 | 2019-03-07 | 2019-04-09 | 2019-09-26 | 2020-02-03 | 2020-03-03 | 2020-03-03
59 | 135 | BB1 | 915 | 2016-11-20 | 2017-01-31 | 18-06-17 | 2017-11-03 | 2017-12-12 | 2017-12-21 | 2020-05-04
60 | 136 | BB2 | 915 | 2016-11-21 | 2017-02-08 | 18-06-17 | 2017-11-03 | 2017-12-12 | 2017-12-21 | 2020-05-04
61 | 137 | BB2 | 1695 | 2017-05-23 | 2017-01-08 | 2018-03-06 | 2019-04-02 | 2019-04-18 | 2019-06-10 | 2019-10-04 | 2019-10-16 | 2019-10-16
62 | 138 | BB2 | 915 | 2017-11-25 | 2018-08-25 | 2018-12-12 | 2019-05-02 | 2019-07-06 | 2019-10-21 | 2020-03-18 | 2021-03-18
63 | 139 | BB2 | 915 | 2018-03-26 | 2017-08-16 | 2018-12-04 | 2019-05-02 | 2019-07-06 | 2019-09-13 | 2019-12-23 | 2020-01-22 | 2020-02-07
64 | 140 | BB2 | 915 | 2018-05-02 | 2018-07-30 | 2018-11-12 | 2019-04-08 | 2019-07-19 | 2020-03-18 | 2020-05-04
65 | 141 | BB2 | 915 | 2018-05-10 | 2018-07-20 | 2018-11-20 | 2019-04-08 | 2019-07-23 | 2019-11-26 | 2019-11-30 | 2019-12-05 | 2019-12-05
66 | 142 | BB2 | 1695 | 2017-11-08 | 2018-04-13 | 2018-10-25 | 2019-03-30 | 2019-05-24 | 2020-04-27 | 2020-06-01
67 | 143 | BB2 | 915 | 2018-01-10 | 2018-04-21 | 2018-09-04 | 2019-03-02 | 2019-05-16 | 2019-08-20 | 2020-01-27 | 2020-02-03 | 2020-02-03
68 | 144 | BB2 | 915 | 2017-08-03 | 2017-12-15 | 2018-08-09 | 2019-03-02 | 2019-05-02 | 2020-01-27 | 2020-01-27 | 2021-02-02
69 | 145 | BB2 | 915 | 2017-03-14 | 2017-07-24 | 2018-07-11 | 2019-06-02 | 2019-07-10 | 2020-01-30 | 2020-06-08
70 | 146 | BB2 | 915 | 2017-11-29 | 2018-04-14 | 2018-11-03 | 2019-06-04 | 2019-07-10 | 2020-01-24 | 2020-02-10 | 2020-02-29 | 2020-02-29
71 | 147 | BB2 | 915 | 2018-05-17 | 2018-08-18 | 2018-11-24 | 2020-07-24 | 2020-10-21
72 | 148 | BB2 | 915 | 2018-03-04 | 2018-08-18 | 2018-11-24 | 2020-06-01 | 2020-10-21
73 | 149 | BB2 | 915 | 2018-03-29 | 2018-09-20 | 2019-09-11 | 2020-06-01 | 2021-01-16
74 | 150 | BB2 | 915 | 2018-03-29 | 2018-10-13 | 2019-07-23 | 2020-06-01 | 2021-01-16
75 | 151 | BB2 | 915 | 2018-05-17 | 2018-10-22 | 2019-06-18 | 2020-06-01 | 2021-01-16
76 | 152 | BB2 | 915 | 2018-08-08 | 2018-10-22 | 2019-06-18 | 2020-06-01 | 2021-01-16
77 | 153 | AA1 | 2170 | 2017-09-02 | 2018-07-25 | 2018-11-16 | 2019-11-20 | 2019-12-12 | 2020-10-27 | 2021-01-16
78 | 154 | AA1 | 1175 | 2017-11-08 | 2018-07-24 | 2018-10-17 | 2019-08-16 | 2020-05-27 | 2020-06-02 | 2020-07-09 | 2021-03-17
79 | 155 | AA1 | 1175 | 2018-01-11 | 2018-07-20 | 2018-10-17 | 2019-08-02 | 2019-09-16 | 2020-02-20 | 2020-07-02 | 2021-02-01
80 | 156 | AA1 | 2170 | 2017-12-15 | 2018-07-09 | 2018-11-16 | 2019-07-26 | 2019-09-08 | 2020-10-10 | 2020-10-21 | 2021-01-18 | 2021-01-22
81 | 157 | AA1 | 1175 | 2017-09-10 | 2018-06-22 | 2018-10-04 | 2019-07-24 | 2019-08-31 | 2020-07-02 | 2020-07-20
82 | 158 | AA1 | 1175 | 31-06-17 | 2018-01-24 | 2018-09-12 | 2019-07-22 | 2019-08-31 | 2020-06-20 | 2020-07-22
83 | 159 | AA1 | 1175 | 2017-11-20 | 2018-01-24 | 2018-09-12 | 2019-07-19 | 2019-08-19 | 2020-06-23 | 2020-08-21
84 | 160 | AA1 | 1175 | 2017-03-14 | 2017-10-07 | 2018-07-19 | 2019-07-16 | 2019-08-05 | 2020-02-20 | 2020-06-08
85 | 161 | AA1 | 1175 | 2018-01-05 | 2018-01-30 | 2018-08-03 | 2019-03-01 | 2019-06-26 | 2019-09-26 | 2020-01-30 | 2021-01-19 | 2021-01-29
86 | 162 | AA1 | 1175 | 2018-02-22 | 2018-03-28 | 2018-07-18 | 2019-03-01 | 2019-06-26 | 2019-10-17 | 2020-06-13
87 | 163 | AA1 | 2170 | 2017-10-24 | 2018-01-27 | 2018-08-03 | 2019-05-29 | 2019-07-19 | 2020-02-10 | 2020-10-21 | 2021-01-20 | 2021-01-25
88 | 164 | AA1 | 2170 | 2017-09-08 | 2017-12-19 | 2018-05-14 | 2019-05-29 | 2019-07-23 | 2020-02-10 | 2020-10-21 | 2021-01-20 | 2021-01-26
89 | 165 | AA1 | 1175 | 2017-08-04 | 2017-08-18 | 2018-01-31 | 2019-03-12 | 2019-06-27 | 2020-07-22 | 2020-09-07
90 | 166 | AA1 | 2170 | 2017-04-05 | 2017-01-08 | 2018-01-23 | 2019-03-12 | 2019-05-27 | 2019-07-22 | 2019-09-08 | 2019-10-29 | 2019-10-29
91 | 167 | AA1 | 1175 | 2017-03-12 | 2017-07-24 | 2017-11-30 | 2019-03-12 | 2019-07-03 | 2020-02-03 | 2020-06-20 | 2021-03-03 | 2021-03-05
92 | 168 | AA2 | 1175 | 2017-11-02 | 2018-02-08 | 2018-09-11 | 2019-12-28 | 2020-02-25 | 2020-08-12 | 2020-09-07 | 2021-02-01 | 2021-02-07
93 | 169 | AA2 | 1175 | 2017-12-18 | 2018-02-08 | 2018-09-28 | 2020-01-24 | 2020-02-25 | 2020-07-22 | 2020-09-07 | 2021-10-10 | 2021-10-12
94 | 170 | AA2 | 2170 | 2018-04-24 | 2018-07-09 | 2018-11-20 | 2020-04-29 | 2020-07-13 | 2020-12-02 | 2020-12-03
95 | 171 | AA2 | 1175 | 2018-05-10 | 2018-07-09 | 2018-10-29 | 2020-01-24 | 2020-02-29 | 2020-12-02 | 2020-12-03
96 | 172 | AA2 | 1175 | 2018-03-15 | 2018-08-01 | 2018-11-24 | 2019-12-18 | 2020-02-29 | 2020-09-15 | 2020-10-10
97 | 173 | AA2 | 1175 | 2017-12-17 | 2018-07-02 | 2018-11-03 | 2019-10-21 | 2020-02-14 | 2020-06-20 | 2020-07-20 | 2021-02-15 | 2021-02-28
98 | 174 | AA2 | 1175 | 2017-11-27 | 2018-01-06 | 2018-08-24 | 2019-08-02 | 2019-09-24 | 2020-02-14 | 2020-06-01 | 2020-06-24 | 2020-07-03
99 | 175 | AA2 | 1175 | 2017-04-30 | 2017-11-25 | 2018-10-03 | 2019-08-14 | 2019-09-24 | 2020-07-02 | 2020-07-25
100 | 176 | AA2 | 1175 | 2018-04-25 | 2018-08-01 | 2018-10-11 | 2019-11-15 | 2020-02-14 | 2020-09-23 | 2020-09-28 | 2021-03-01 | 2021-03-03
101 | 177 | AA2 | 1175 | 2017-12-28 | 2018-08-11 | 2018-12-28 | 2020-02-10 | 2020-03-18 | 2020-07-22 | 2020-09-15 | 2021-01-01 | 2021-01-08
102 | 178 | AA2 | 1175 | 2018-02-15 | 2018-09-05 | 2018-11-28 | 2019-12-28 | 2020-03-18 | 2020-07-25 | 2020-10-10
103 | 179 | AA2 | 1175 | 2018-05-16 | 2018-11-20 | 2019-02-18 | 2019-12-12 | 2020-01-06 | 2020-02-10 | 2020-06-23 | 2020-07-15 | 2020-07-24
104 | 180 | AA2 | 2170 | 2018-06-03 | 2018-11-24 | 2019-05-22 | 2019-12-15 | 2020-05-28 | 2020-12-21 | 2020-12-21
105 | 181 | AA2 | 1175 | 2018-11-02 | 2018-11-27 | 2019-05-22 | 2019-12-15 | 2020-02-20 | 2020-07-28 | 2020-09-02
106 | 182 | AA2 | 1175 | 2017-12-26 | 2019-01-29 | 2019-05-22 | 2019-12-12 | 2020-02-03 | 2020-07-24 | 2020-09-10
107 | 183 | AA1 | 2170 | 2018-12-31 | 2019-12-13 | 2019-08-16 | 2020-01-23 | 2020-07-20 | 2020-12-21 | 2020-12-27
108 | 184 | AA1 | 2170 | 2018-12-29 | 2019-02-13 | 2019-08-07 | 2020-01-23 | 2020-07-04 | 2020-09-07 | 2020-09-10
109 | 185 | AA1 | 2170 | 2018-12-10 | 2019-02-06 | 2019-08-07 | 2019-12-24 | 2020-07-20 | 2020-12-02 | 2020-12-21
Note: Send report every Thursday.

## Anx - E -Estimate of work done
Annexure - E - Circular no. 807(b)
Estimate of work done
Name of contractor: |  |  |  | Home Line Infra
Company name: |  |  |  | Nilgiri Estate
Project name: |  |  |  | Nilgiri Estates
Date: |  |  |  | 2021-06-11
[9 empty] | Const. Contract Rate: |  | 720
|  | Rate |  |  | 20 | 25 | 25 | 20 | 10 | 100 | 720
S No | Villa no. | Type (2, 3, 4 BHK) | SBUA | Work start date | Earth work, footing, plinth, column1 | RRC, slabs + head room | Brick work, compound wall & site levelling | 2 coats plastering | Final finishing and handover | Total percentage of work done | Construction contract value | Value of work done | Advance Paid | Advance adjusted | Balance payable
1 | 80 A | 2BHK | 1205 | 2016-05-12 | 1 | 1 | 1 | 1 | 0 | 90 | 867600 | 780840 | 100000 | 90000 | 690840
2 | 80 B | 2BHK | 1205 | 2016-12-28 | 1 | 1 | 1 | 1 | 0 | 90 | 867600 | 780840 | 100000 | 90000 | 690840
3 | 80 C | 2BHK | 1215 | 2017-06-05 | 1 | 1 | 1 | 1 | 0 | 90 | 874800 | 787320 | 100000 | 90000 | 697320
4 | 80 D | 2BHK | 1215 | 2016-12-12 | 1 | 1 | 1 | 1 | 0 | 90 | 874800 | 787320 | 100000 | 90000 | 697320
5 | 81 | 2BHK | 1175 | 2016-11-14 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
6 | 82 | 2BHK | 1175 | 2016-11-05 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
7 | 83 | 2BHK | 1175 | 2016-11-07 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
8 | 84 | 2BHK | 1175 | 2016-11-08 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
9 | 85 | 2BHK | 1175 | 2016-12-19 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
10 | 86 | 2BHK | 1175 | 2017-01-20 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
11 | 87 | 2BHK | 1175 | 2016-12-02 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
12 | 88 | 2BHK | 1175 | 2016-12-08 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
13 | 89 | 2BHK | 2170 | 2017-06-15 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
14 | 90 | 2BHK | 1175 | 2017-06-05 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
15 | 91 | 2BHK | 1175 | 2017-01-02 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
16 | 92 | 2BHK | 1175 | 2016-11-10 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
17 | 93 | 2BHK | 1175 | 2016-11-11 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
18 | 94 | 2BHK | 1175 | 2016-12-17 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
19 | 95 | 2BHK | 1175 | 2016-12-14 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
20 | 96 | 2BHK | 1175 | 2017-01-03 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
21 | 97 | 2BHK | 1175 | 2017-01-18 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
22 | 98 | 2BHK | 1175 | 2017-02-10 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
23 | 99 | 2BHK | 1175 | 2016-12-21 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
24 | 100 | 4BHK | 2170 | 2016-11-22 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
25 | 101 | 2BHK | 1175 | 2017-01-19 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
26 | 102 | 2BHK | 1175 | 2017-12-14 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
27 | 103 | 2BHK | 1175 | 2018-02-15 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
28 | 104 | 2BHK | 1175 | 2017-11-14 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
29 | 105 | 2BHK | 1175 | 2018-02-21 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
30 | 106 | 2BHK | 1175 | 2017-12-12 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
31 | 107 | 2BHK | 1175 | 2017-10-18 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
32 | 108 | 2BHK | 1175 | 2017-02-08 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
33 | 109 | 3BHK | 2170 | 2017-06-05 | 0 | 1 | 1 | 1 | 0 | 70 | 1562400 | 1093680 | 100000 | 70000 | 1023680
34 | 110 | 2BHK | 1175 | 2017-06-20 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
35 | 111 | 2BHK | 1175 | 2017-01-02 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
36 | 112 | 2BHK | 1175 | 2017-01-03 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
37 | 113 | 2BHK | 1175 | 2017-03-03 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
38 | 114 | 4BHK | 2170 | 2017-02-07 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
39 | 115 | 2BHK | 1175 | 2017-01-12 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
40 | 116 | 3BHK | 2170 | 2017-01-13 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
41 | 117 | 2BHK | 1175 | 2017-12-28 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
42 | 118 | 2BHK | 1175 | 2017-03-08 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
43 | 119 | 2BHK | 915 | 2017-02-01 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
44 | 120 | 2BHK | 915 | 2017-02-08 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
45 | 121 | 2BHK | 915 | 2017-02-09 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
46 | 122 | 2BHK | 915 | 2017-03-08 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
47 | 123 | 3BHK | 1695 | 2017-05-25 | 1 | 1 | 1 | 1 | 0 | 90 | 1220400 | 1098360 | 100000 | 90000 | 1008360
48 | 124 | 2BHK | 915 | 2017-04-04 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
49 | 125 | 2BHK | 915 | 2017-03-08 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
50 | 126 | 2BHK | 915 | 2017-02-08 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
51 | 127 | 2BHK | 915 | 2017-08-03 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
52 | 128 | 2BHK | 915 | 2018-01-10 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
53 | 129 | 2BHK | 915 | 2018-04-25 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
54 | 130 | 2BHK | 915 | 2018-08-08 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
55 | 131 | 2BHK | 915 | 2018-07-04 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
56 | 132 | 2BHK | 915 | 2018-06-14 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
57 | 133 | 2BHK | 915 | 2017-04-06 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
58 | 134 | 2BHK | 915 | 2017-02-18 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
59 | 135 | 2BHK | 915 | 2016-11-20 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
60 | 136 | 2BHK | 915 | 2016-11-21 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
61 | 137 | 3BHK | 1695 | 2017-05-23 | 1 | 1 | 1 | 1 | 0 | 90 | 1220400 | 1098360 | 100000 | 90000 | 1008360
62 | 138 | 2BHK | 915 | 2017-11-25 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
63 | 139 | 2BHK | 915 | 2018-03-26 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
64 | 140 | 2BHK | 915 | 2018-05-02 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
65 | 141 | 2BHK | 915 | 2018-05-10 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
66 | 142 | 2BHK | 1695 | 2017-11-08 | 1 | 1 | 1 | 1 | 0 | 90 | 1220400 | 1098360 | 100000 | 90000 | 1008360
67 | 143 | 2BHK | 915 | 2018-01-10 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
68 | 144 | 2BHK | 915 | 2017-08-03 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
69 | 145 | 2BHK | 915 | 2017-03-14 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
70 | 146 | 2BHK | 915 | 2017-11-29 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
71 | 147 | 2BHK | 915 | 2018-05-17 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
72 | 148 | 2BHK | 915 | 2018-03-04 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
73 | 149 | 2BHK | 915 | 2018-03-29 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
74 | 150 | 2BHK | 915 | 2018-03-29 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
75 | 151 | 2BHK | 915 | 2018-05-17 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
76 | 152 | 2BHK | 915 | 2018-08-08 | 1 | 1 | 1 | 1 | 0 | 90 | 658800 | 592920 | 100000 | 90000 | 502920
77 | 153 | 2BHK | 2170 | 2017-09-02 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
78 | 154 | 2BHK | 1175 | 2017-11-08 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
79 | 155 | 2BHK | 1175 | 2018-01-11 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
80 | 156 | 3BHK | 2170 | 2017-12-15 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
81 | 157 | 2BHK | 1175 | 2017-09-10 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
82 | 158 | 2BHK | 1175 | 31-06-17 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
83 | 159 | 2BHK | 1175 | 2017-11-20 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
84 | 160 | 2BHK | 1175 | 2017-03-14 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
85 | 161 | 2BHK | 1175 | 2018-01-05 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
86 | 162 | 2BHK | 1175 | 2018-02-22 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
87 | 163 | 4BHK | 2170 | 2017-10-24 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
88 | 164 | 3BHK | 2170 | 2017-09-08 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
89 | 165 | 2BHK | 1175 | 2017-08-04 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
90 | 166 | 3BHK | 2170 | 2017-04-05 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
91 | 167 | 2BHK | 1175 | 2017-03-12 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
92 | 168 | 2BHK | 1175 | 2017-11-02 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
93 | 169 | 2BHK | 1175 | 2017-12-18 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
94 | 170 | 2BHK | 2170 | 2018-04-24 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
95 | 171 | 2BHK | 1175 | 2018-05-10 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
96 | 172 | 2BHK | 1175 | 2018-03-15 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
97 | 173 | 2BHK | 1175 | 2017-12-17 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
98 | 174 | 2BHK | 1175 | 2017-11-27 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
99 | 175 | 2BHK | 1175 | 2017-04-30 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
100 | 176 | 2BHK | 1175 | 2018-04-25 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
101 | 177 | 2BHK | 1175 | 2017-12-28 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
102 | 178 | 2BHK | 1175 | 2018-02-15 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
103 | 179 | 2BHK | 1175 | 2018-05-16 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
104 | 180 | 2BHK | 2170 | 2018-06-03 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
105 | 181 | 2BHK | 1175 | 2018-12-26 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
106 | 182 | 3BHK | 1175 | 2017-12-26 | 1 | 1 | 1 | 1 | 0 | 90 | 846000 | 761400 | 100000 | 90000 | 671400
107 | 183 | 3BHK | 2170 | 2018-12-31 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
108 | 184 | 3BHK | 2170 | 2018-12-29 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
109 | 185 | 4BHK | 2170 | 2018-12-10 | 1 | 1 | 1 | 1 | 0 | 90 | 1562400 | 1406160 | 100000 | 90000 | 1316160
|  |  | 136640 |  | 108 | 109 | 109 | 109 | 0 | 9790 | 98380800 | 88230240 | 10900000 | 9790000 | 78440240
Note: Send report every Thursday. | [9 empty] | A | Amount paid to contractor |  |  |  | 97276683
[10 empty] | B | Less: Advance paid |  |  |  | 10900000
[10 empty] | C | Balance payable to contractor |  |  |  | -7936443