## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-06-19
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing 8mm toughness | Document is Estimation
177482 | 18.03.2021 | Kitchen unit | Quotes to be receive
177483 | 18.03.2021 | Kitchen unit | Quotes to be receive
177484 | 18.03.2021 | Kitchen unit | Quotes to be receive
177485 | 18.03.2021 | Kitchen unit | Quotes to be receive
177486 | 18.03.2021 | Kitchen unit | Quotes to be receive
177492 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177493 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177497 | 19.03.2021 | Grills part 2 | Po to be issue
177502 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177503 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177588 | 17.04.2021 | Waterproofing | Document is in estimation
177651 | 17.05.2021 | Main door beeding | Document is in estimation
177682 | 01.06.2021 | Transformer to 800Amps | PO 77713
177683 | 01.06.2021 | Copper plate,Gi pipe,Bentonite powder,nut bolts | PO 77651,77652
177692 | 03.06.2021 | Fire door | Comparision with MDS for Approval
177711 | 07.06.2021 | Thandor stone | PO 77813
177721 | 10.06.2021 | Generator | Comparision with MDS for Approval
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177387 | 16.02.2021 | Upvc sliding windows | Work under progress
177404 | 24.02.2021 | Grills 2x2 | NO stock at supplier
177447 | 11.03.2021 | Concrete grigio | No stock at supplier SSLLP
177472 | 17.03.2021 | Down commers, sprinklers | Work under progress
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478&177479 | 17.03.2021 | Pannel doors part 1 | Delivery as per po given in parts
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Delivery as per po given in parts
177488 | 18.03.2021 | MCBs,modular plate ,socket | Delivery as per po given in parts
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177491 | 18.03.2021 | Grills part 1 | Delivery as per po given in parts
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177498 | 19.03.2021 | Stainless steel sink | Supplier arrange the material delivered by next week
177513 | 20.03.2021 | Spring wire, Tv wire, telephone wire ,Internet cable | Part material deliverd balance as per the request of site in parts
177544 | 31.03.2021 | Doors beeding | Pick up from SSLLP
177557 | 06.04.2021 | Luna ,ultra , Malaysian lt,dk, hl | Pick up from SSLLP
177563 | 06.04.2021 | Kitchen dado,utility floor tiles | Pick up from SSLLP
177564 | 06.04.2021 | Ms Railing | Under fabrication
177582 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Part material delivered, balance will be delivered by the 1 st week of july
177591 | 20.04.2021 | AMC for Generator Set | Work under progress
177597 | 23.04.2021 | Bath room tiles | Pick up from SSLLP
177599 | 24.04.2021 | Grigio serena, concrete beige & concrete grigio | Awaiting to receive the stock
177608 | 26.04.2021 | DB 3 phase | Pick up from SSLLP
177630 | 04.05.2021 | MS grills | Under fabrication
177639 | 06.05.2021 | Plasticizer | Part material delivered, balance pick up from ssllp
177642 | 08.05.2021 | Kitchen unit | Cancelled as supplier not willing to do
177657 | 21.05.2021 | Pvc Pipes | Delivered
177660 | 28.05.2021 | Tube light | Delivered
177683 | 01.06.2021 | RCC Rings&RCC gully Trap Cover | Delivered
177684 | 01.06.2021 | Z angle Templates | Delivered
177689 | 02.06.2021 | MS L angle brackets | Supplier Arrange the Material delivered by next week
177690 | 03.06.2021 | Curb stone | Supplier will deliver the material
177693 | 03.06.2021 | Flush doors | Supplier will deliver the material
177702 | 05.06.2021 | DB box 3 phase | Delivered
177705 | 07.06.2021 | Cutting wheel | Delivered
177707 | 07.06.2021 | MS box pipe 2.5mm | Delivered
177708 | 07.06.2021 | Aluminium Service wire ,Tv wire | Delivered
177712 | 08.06.2021 | Kitchen unit | Work under progress
177713 | 06.06.2021 | Kitchen unit | Work under progress
177714 | 08.06.2021 | Kitchen unit | Work under progress
177716 | 08.06.2021 | CERA anchorset | Delivered
177717 | 08.06.2021 | RCC Rings&RCC gully Trap Cover | Delivered
177727 | 14.06.2021 | Steel gray Granit | Delivered
177728 | 15.06.2021 | Janata paste ,Araldite | Delivered
177729 | 15.06.2021 | Cement hume pipe | Delivered