## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-06-21
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163538 | 2021-06-09 | Electronic motor | Cancelled issued another req 182960
163520 | 2021-06-04 | Fire rated doors | Cancelled
163513 | 2021-06-03 | Tandoor stone | PO to be issue
163512 | 2021-06-03 | Coffee powder and Tea | Local purchase
163460 | 2021-04-27 | Camera | Oderderd in amazon awaiting for delivery
163518 | 2021-06-04 | Wifi router | PO 77965
163546 | 2021-06-14 | Air cooled serew chillers | PO to be issue
163547 | 2021-06-15 | Safety instructions boards | Cancelled
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163510 | 2021-06-03 | Tiles | By next week part material will be delivered
163534 | 2021-06-08 | Caution ribbon | Awaiting to receive the material from vendor
163517 | 2021-06-04 | Cables | Contact premier engineering for delivery
163532 | 2021-06-08 | Grinding blades rod cutting bocsh cutting machine | Delivered
163531 | 2021-06-08 | Astradge rubbrised tape | As per MD instructions 1 nos to be delivered to sites
163536 | 2021-06-09 | Panels 33 KV VCB | Supplier will deliver directly
163529 | 2021-06-08 | Scribbling pads | Pick up from SSLLP
163543 | 2021-06-10 | Spade with handle | Pick up from SSLLP
163545 | 2021-06-12 | Safety shoes | Delivered
163552 | 2021-06-16 | Self priming dewatering pump 1 HP | Delivered
163553 | 2021-06-16 | Self priming dewatering pump 3 HP | Delivered
156554 | 2021-06-16 | Self priming dewatering pump 5 HP | Delivered
163555 | 2021-06-16 | Green Hose pipe | Pick up from Supplier