## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estates
Site: |  | 2021-06-19
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
175250 | 2021-04-10 | Parking benches | Estimate to be prepare
175279 | 2021-05-07 | BT Road patching | Enquiry in market
175281 | 2021-05-11 | Laptop bags | Online purchase
175296 | 2021-06-16 | PVC pipes and Commode sheet cover | PO 77986
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
175252 | 2021-04-10 | Fire exetinguisher | Delivered
175260 | 2021-04-17 | Aerocon pannels | Cancelled by MD
175285 | 2021-06-13 | Panel doors | Delivered
175285 | 2021-05-19 | Boom barrier | Req no wrong ckeck and send correctly
175291 | 2021-06-09 | Altek lappum | Delivered
175293 | 2021-06-09 | Plastic chairs | Supplier will deliver
175295 | 2021-06-16 | Tandoor stone | Pick up from SSLLP
175297 | 2021-06-16 | Vitrified tiles | Pick up from Vista