## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-06-26
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing 8mm toughness | Document is Estimation
177482 | 2021-03-18 | Kitchen Unit | Cancelled and issued on other requisition
177483 | 2021-03-18 | Kitchen Unit | Cancelled and issued on other requisition
177484 | 2021-03-18 | Kitchen Unit | Cancelled and issued on other requisition
177485 | 2021-03-18 | Kitchen Unit | Cancelled and issued on other requisition
177486 | 2021-03-18 | Kitchen Unit | Cancelled and issued on other requisition
177492 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177493 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177497 | 19.03.2021 | Grills part 2 | Po to be issue
177502 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177503 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177588 | 17.04.2021 | Waterproofing | PO 76655
177683 | 01.06.2021 | Copper plate,Gi pipe,Bentonite powder,nut bolts | PO 77651, 77652
177692 | 03.06.2021 | Fire door | Comparision with MDS for Approval
177711 | 07.06.2021 | Thandor stone | PO 77813
177721 | 10.06.2021 | Generator | Under negotiation
177745 | 19.06.2021 | Transformer cables | PO 77870
177752 | 22.06.2021 | MCB,ECCB 4 pole,2pole | PO 78059
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177387 | 16.02.2021 | Upvc sliding windows | Work under progress
177404 | 24.02.2021 | Grills 2x2 | Deliverd
177447 | 11.03.2021 | Concrete grigio | Collect from GMR
177472 | 17.03.2021 | Down commers, sprinklers | Work under progress
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478&177479 | 17.03.2021 | Pannel doors part 1 | Half of the material we received remaining supplier arrange the material delivered by next week
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177488 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177491 | 18.03.2021 | Grills part 1 | Half of the material we received remaining material supplier arrange the material delivered by next week SSLLP
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177498 | 19.03.2021 | Stainless steel sink | Supplier arrange the material delivered by next week
177513 | 20.03.2021 | Spring wire, Tv wire, telephone wire ,Internet cable | Supplier Arrange the Material Delivered by next week
177544 | 31.03.2021 | Doors beeding | will pick up from SSLLP next week
177557 | 06.04.2021 | Luna ,ultra , Malaysian lt,dk, hl | Half of the material we received remaining we will pick up from SSLLP next wee
177563 | 06.04.2021 | Kitchen dado,utility floor tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177564 | 06.04.2021 | Ms Railing | Under fabrication
177582 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Half of the material we received remaining material supplier arrange the material delivered by next week
177591 | 20.04.2021 | AMC for Generator Set | Work under progress
177597 | 23.04.2021 | Bath room tiles | Half of the material we received remaining we will pick up from SSLLP next week
177599 | 24.04.2021 | Grigio serena, concrete beige & concrete grigio | Half of the material we received remaining we will pick up from GMR site
177608 | 26.04.2021 | DB 3 phase | Collect from SSLLP
177630 | 04.05.2021 | MS grills | Under fabrication
177639 | 06.05.2021 | Plasticizer | Half of the material we received remaining we will pick up from SSLLP next week
177642 | 08.05.2021 | Kitchen unit | Supplier Arrange the material delivered by next week
177684 | 01.06.2021 | Z angle Templates | Half of the material we received remaining we will pick up from SSLLP next week
177689 | 02.06.2021 | MS L angle brackets | Supplier Arrange the Material delivered by next week
177690 | 03.06.2021 | Curb stone | Under fabrication
177693 | 03.06.2021 | Flush doors | Supplier Arrange the Material delivered by next week
177712 | 08.06.2021 | Kitchen unit | Work under progress
177713 | 06.06.2021 | Kitchen unit | Work under progress
177714 | 08.06.2021 | Kitchen unit | Work under progress
177717 | 08.06.2021 | RCC Rings | Material is ready We will pick from SSLLP on Monday
177718 | 10.06.2021 | Tan brown Granite | Under Fabrication
177728 | 15.06.2021 | Grout ,Roff chemical | Partially delivered
177736 | 18.06.2021 | Regal beige | Half of the material we received remaining we will pick up from GMR next week
177737 | 18.06.2021 | Inwall Tank | Half of the material we received remaining we will pick up from SSLLP next week
177739 | 18.06.2021 | Pvc pipes | Half of the material delivered remaining we will pick up from SSLLP next week
177740 | 18.06.2021 | CPVC pipes | Deliverd
177742 | 19.06.2021 | PVC 1.2mm Pipe | Deliverd
177743 | 19.06.2021 | Drain Pipe Chambers | Deliverd
177746 | 19.06.2021 | SS Name plates 4’’x4’’ | Under fabrication
177747 | 19.06.2021 | SS Name Plates 6’’x6’’ | Under fabrication
177748 | 22.06.2021 | Janata paste,Roff chemical grouts | Deliverd
177749 | 22.06.2021 | Tan brown Granite | Pick up from SOV
177750 | 22.06.2021 | Tan brown Granite | Pick up from SOV
177751 | 22.06.2021 | Pens /etc | Part deliverd balance pick up from SSLLP