## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estates
Site: |  | 2021-06-26
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
175250 | 2021-04-10 | Parking benches | Estimate to be prepare
175279 | 2021-05-07 | BT Road patching | PO 78182
175281 | 2021-05-11 | Laptop bags | Online purchase
175298 | 2021-06-19 | CP Fittings | PO 78072
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
175293 | 2021-06-09 | Plastic chairs | PO to be issue
175295 | 2021-06-16 | Tandoor stone | Pick up from SSLLP