## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-06-26
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163575 | 2021-06-23 | Safety boards | Promotions to follow up.
163573 | 2021-06-23 | MS Square pipe and MS Flat patti | PO 78131
163569 | 2021-06-23 | RMC | PO 78026
163558 | 2021-06-17 | Torchlights and umbrellas | PO 78137, 78138
163514 | 2021-06-25 | ACs remote and tripod- Battries | Online purchase
163513 | 2021-06-03 | Tandoor stone | Cancelled by md.
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163577 | 2021-06-24 | Gova rope and green curing pipes | Deliverd
163579 | 2021-06-23 | Measuring tapes | Deliverd
163576 | 2021-06-23 | Solid bricks | Supplier will directly deliver as per the site requirment
163572 | 2021-06-22 | Solid bricks | Supplier will directly deliver as per the site requirment
163571 | 2021-06-22 | Starters | Deliverd
163567 | 2021-06-21 | Z Angles | Collect from SSLLP
163563 | 2021-06-19 | MS Templates | Collect from SSLLP
163559 | 2021-06-18 | CC Templates | Local purchase
163555 | 2021-06-16 | Green hose pipe | Deliverd
163543 | 2021-06-10 | Spade with handle | Deliverd
163534 | 2021-06-08 | Caution ribbon | Part deliverd, balance pick up from SSLLP
163517 | 2021-06-04 | Gloster cables | Collect from Premier
163512 | 2021-06-03 | Coffee powder and lemon tea powder | Local purchase
163510 | 2021-06-03 | Tiles | PO issued co ordinate with Team Hestia-7386645663
163460 | 2021-04-27 | Cannon camera | Pick up from SSLLP
163418 | 2021-03-24 | Curb stone | Deliverd