## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-07-03
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
180630 | 2021-02-11 | Al sliding windows | Delivered
180876 | 2021-05-10 | Tan brown granite | Pick up from SOVLLP
180799 | 2021-06-09 | Causurina plants | Supplier will deliver directly
180794 | 2021-06-09 | Cleaning material | Delivered