## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Modi Realty Pocharam LLP(NGH)
Site: |  | 2021-07-03
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where where PO/WO not prepared 3 working days after requisition
181574 | 2021-05-07 | Battary vehicle | Req with MD for approval
181576 | 2021-05-10 | Pulse oxy meter | Purchase locally, remove from this list
181577 | 2021-05-11 | Laptop | Co ordinate with laxmi sys admin
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
181595 | 2021-06-14 | Notice board | Co ordinatw with supplier Anand
181588 | 2021-06-12 | Starter | Deliverd