## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-07-10
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163612 | 2021-07-08 | Blank Cinder | PO 78456
163611 | 2021-07-08 | MS L angle | PO 78666
163608 | 2021-07-05 | AMC For RO plant | PO 78698
163607 | 2021-07-05 | Holes packing chemicals | Hold By MD
163586 | 2021-06-26 | Birla wall care putty | PO 78514
163585 | 2021-06-30 | Electrical Bike | PO to be issue
163602 | 2021-06-30 | 200 NB GI pipe | Cancelled
163601 | 2021-06-30 | 33 KV Cable | PO 78451
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163610 | 2021-07-07 | Blue sheets, tube lights | Pick up from SSLLP
163605 | 2021-07-03 | Biometric machine | Collect from Supplier Interactive
163603 | 2021-07-03 | Rain coats | Delivered
163598 | 2021-06-29 | Tandoor stone | Pick up from SSLLP
163579 | 2021-06-24 | Steel measuring tape | Delivered
163600 | 2021-06-30 | Fire safety system | Work order, kindly remove from this remarks
163583 | 2021-06-26 | HT metering cubicle | Co ordinate with supplier
163580 | 2021-06-25 | Sand stone lt grey- Tiles | Next month delivery as parts
163568 | 2021-06-22 | 250 DG Set | Co ordinate with supplier
163567 | 2021-06-21 | Z Angles | Pick up from SSLLP
163561 | 2021-06-19 | 33KV indoor ICOG Panel | Co ordinate with supplier
163562 | 2021-06-19 | LT Panels | Co ordinate with supplier
163563 | 2021-06-19 | MS Templates | Pick up from SSLLP
163558 | 2021-06-17 | Torch lights and umbrellas | Delivered
163546 | 2021-06-14 | Air cooled screw chillers | PO Not issued contact waseem
163536 | 2021-06-09 | 33 KV VCB Switch board | Co ordinate with supplier
163534 | 2021-06-08 | Caution ribbon | Delivered