## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-07-10
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing 8mm toughness | Document is Estimation
177482 | 18.03.2021 | Kitchen unit | Quotes to be receive
177483 | 18.03.2021 | Kitchen unit | Quotes to be receive
177484 | 18.03.2021 | Kitchen unit | Quotes to be receive
177485 | 18.03.2021 | Kitchen unit | Quotes to be receive
177486 | 18.03.2021 | Kitchen unit | Quotes to be receive
177492 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177493 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177502 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177503 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177588 | 17.04.2021 | Waterproofing | Document is in estimation
177692 | 03.06.2021 | Fire door | Comparision with MDS for Approval
177721 | 10.06.2021 | Generator | Comparision with MDS for Approval
177762 | 28.06.2021 | Fire doors | Clarification required
177769 | 30.06.2021 | Grills part 2 | Hold by MD
177770 | 30.06.2021 | Grills part 2 | Hold by MD
177771 | 30.06.2021 | Grills part 2 | Hold by MD
177772 | 30.06.2021 | Grills part 2 | Hold by MD
177777 | 01.07.2021 | Ply wood sheet | PO 78743
177784 | 03.07.2021 | Generator distribution panel | Cancelled by MD
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177387 | 16.02.2021 | Upvc sliding windows | Work under progress
177404 | 24.02.2021 | Grills 2x2 | Material is ready we will pick up on Monday
177447 | 11.03.2021 | Concrete grigio | Material is ready we will from GMR next week
177472 | 17.03.2021 | Down commers, sprinklers | Work under progress
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478&177479 | 17.03.2021 | Pannel doors part 1 | Half of the material we received remaining supplier arrange the material delivered by next week
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177488 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177491 | 18.03.2021 | Grills part 1 | Half of the material we received remaining material supplier arrange the material delivered by next week SSLLP
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177498 | 19.03.2021 | Stainless steel sink | Supplier arrange the material delivered by next week
177513 | 20.03.2021 | Spring wire, Tv wire, telephone wire ,Internet cable | Supplier Arrange the Material Delivered by next week
177559 | 06.04.2021 | Bathroom tiles luna ultra malaysian | Half of the material we received remaining material supplier arrange the material delivered by next week
177562 | 06.04.2021 | Vertrified tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177582 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Half of the material we received remaining material supplier arrange the material delivered by next week
177591 | 20.04.2021 | AMC for Generator Set | AMC its work under process
177597 | 23.04.2021 | Bath room tiles | Half of the material we received remaining we will pick up from SSLLP next week
177599 | 24.04.2021 | Grigio serena, concrete beige & concrete grigio | Half of the material we received remaining we will pick up from GMR site
177630 | 04.05.2021 | MS grills utility | Under fabrication
177642 | 08.05.2021 | Kitchen unit | Cancelled by MD
177651 | 17.05.2021 | Doors beeding | Supplier Arrange the Material delivered by next week
177683 | 01.06.2021 | RCC rings | Material is Ready We will pick up on Monday
177684 | 01.06.2021 | Z angle Templates 3’x2’ | Half of the material we received remaining we will pick up from SSLLP next week
177690 | 03.06.2021 | Curb stone | Half of the material received remaining supplier arrange Material delivered by next week
177693 | 03.06.2021 | Flush doors | No stock at supplier
177711 | 07.06.2021 | Thandor stone | Half of the material received remaining supplier arrange Material delivered by next week
177717 | 08.06.2021 | RCC Rings | Material is ready We will pick from SSLLP on Monday
177719 | 10.06.2021 | CLC Blocks | No stock at supplier
177746 | 19.06.2021 | SS Name plates 4’’x4’’ | Under fabrication
177747 | 19.06.2021 | SS Name Plates 6’’x6’’ | Under fabrication
177748 | 22.06.2021 | Janata paste,Roff chemical grouts | Partially delivered
177751 | 22.06.2021 | Pens | Deliverd
177753 | 22.06.2021 | MS round pipes | Deliverd
177757 | 25.06.2021 | General items sponges,mopping sticks | Deliverd
177759 | 25.06.2021 | Curing pipe | Deliverd
177765 | 28.06.2021 | Wipro LED lights | Deliverd
177766 | 28.06.2021 | Gi flat patti | Deliverd
177767 | 30.06.2021 | MS flat patti | Deliverd
177778 | 01.07.2021 | PVC false ceiling | Co ordinate with supplier
177783 | 03.07.2021 | CPVC pipe 10ft length | Deliverd
177787 | 03.07.2021 | Manhole round covers | Pick up from supplier