## SOVLLP
Prepared by: | Bhavani
Report Date | 08.05.2021
Site | Manila Mod Memorial hospital
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
Nil | Nil | Nil | Nil
List of requisitions Where PO/WO is prepared and items have not received at site
162102 | 27.04.2021 | Templets | Collect From SSLLP