## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-07-17
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing 8mm toughness | Document is Estimation
177482 | 18.03.2021 | Kitchen unit | Cancelled issude another requisition to KBD
177483 | 18.03.2021 | Kitchen unit | Cancelled issude another requisition to KBD
177484 | 18.03.2021 | Kitchen unit | Cancelled issude another requisition to KBD
177485 | 18.03.2021 | Kitchen unit | Cancelled issude another requisition to KBD
177486 | 18.03.2021 | Kitchen unit | Cancelled issude another requisition to KBD
177492 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177493 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177502 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177503 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177588 | 17.04.2021 | Waterproofing | Document is in estimation
177721 | 10.06.2021 | Generator | Comparision with MDS for Approval
177762 | 28.06.2021 | Fire doors | PO 78750
177769 | 30.06.2021 | Grills part 2 | Hold by MD
177770 | 30.06.2021 | Grills part 2 | Hold by MD
177771 | 30.06.2021 | Grills part 2 | Hold by MD
177772 | 30.06.2021 | Grills part 2 | Hold by MD
177777 | 01.07.2021 | Ply wood sheet | PO 78743
177784 | 03.07.2021 | Generator distribution panel | Cancelled.
177799 | 08.07.2021 | Ms pipe | PO 78660, 78681, 78794
177800 | 08.07.2021 | PVC Rigid pipes | Cancelled
177802 | 10.07.2021 | Air blower | Online Purchase
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177387 | 16.02.2021 | Upvc sliding windows | Work under progress
177404 | 24.02.2021 | Grills 2x2 | Material is ready we will pick up on Monday
177447 | 11.03.2021 | Concrete grigio | Material is ready we will from GMR next week
177472 | 17.03.2021 | Down commers, sprinklers | Work under progress
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478&177479 | 17.03.2021 | Pannel doors part 1 | Half of the material we received remaining supplier arrange the material delivered by next week
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177488 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177491 | 18.03.2021 | Grills part 1 | Half of the material we received remaining material supplier arrange the material delivered by next week SSLLP
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177498 | 19.03.2021 | Stainless steel sink | Supplier arrange the material delivered by next week
177513 | 20.03.2021 | Spring wire, Tv wire, telephone wire ,Internet cable | Half of the material we received remaining supplier arrange the material material by partially
177559 | 06.04.2021 | Bathroom tiles luna ultra malaysian | Half of the material we received remaining material supplier arrange the material delivered by next week
177562 | 06.04.2021 | Vertrified tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177582 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Half of the material we received remaining material supplier arrange the material delivered by next week
177591 | 20.04.2021 | AMC for Generator Set | Work under progress
177597 | 23.04.2021 | Bath room tiles | Half of the material we received remaining we will pick up from SSLLP next week
177642 | 08.05.2021 | Kitchen unit | Work under progress
177651 | 17.05.2021 | Doors beeding | Supplier Arrange the Material delivered by next week
177684 | 01.06.2021 | Z angle Templates 3’x2’ | Half of the material we received remaining we will pick up from SSLLP next week
177690 | 03.06.2021 | Curb stone | Half of the material received remaining supplier arrange Material delivered by next week
177693 | 03.06.2021 | Flush doors | Co ordinate with supplier Sri Balaji
177711 | 07.06.2021 | Thandor stone | Half of the material received remaining supplier arrange Material delivered by next week
177746 | 19.06.2021 | SS Name plates 4’’x4’’ | Under fabrication
177747 | 19.06.2021 | SS Name Plates 6’’x6’’ | Under fabrication
177751 | 22.06.2021 | Pens | Deliverd
177753 | 22.06.2021 | MS round pipes | Half of the Material is received ,remaining suppliers arranging the material next week
177757 | 25.06.2021 | General items sponges,mopping sticks | Deliverd
177766 | 28.06.2021 | Gi flat patti | Partially delivered
177767 | 30.06.2021 | MS flat patti | Supplier arrange in the material delivered by next week
177778 | 01.07.2021 | PVC false ceiling | Supplier delivered after received the payment
177787 | 03.07.2021 | Manhole round covers | Supplier arrange the material delivered by next week
177789 | 06.07.2021 | Sadar ali Grey Granite | Supplier Arrange The material delivered by next week
177793 | 07.07.2021 | Cpvc Pipes | Deliverd
177794 | 07.07.2021 | PVC pipes | Deliverd
177796 | 07.07.2021 | Fishers | Deliverd
177803 | 10.07.2021 | Tiles grout ,chemical ,roff chemical | Partially delivered