## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-07-17
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163624 | 2021-07-15 | Canvas hose pipe | PO 78655
163623 | 2021-07-14 | Rain coat, umbrellas | PO 78764
163622 | 2021-07-14 | Bamboo thadka | Locally purchased by site can be closed
163607 | 2021-07-05 | Holes packing chemicals | Cancelled by MD
163585 | 2021-06-26 | Elecrric bike | PO 78877
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163625 | 2021-07-15 | Coffee powder and Tea Powder | PO made wrongly to regular supplier, cancell and send another requisition
163621 | 2021-07-14 | Armourd boards | Deliverd
163617 | 2021-07-12 | White boards, blue pens | Pick up from SSLLP
163614 | 2021-07-08 | Expensive morter | Co ordinate with supplier
163612 | 2021-07-08 | Black cinder | Deliverd
163610 | 2021-07-07 | Blue sheets | Deliverd
163605 | 2021-07-03 | Biometric machine | Co ordinate with supplier
163598 | 2021-06-29 | Tandoor stone | Direct supplier will send to site by next week
163579 | 2021-06-24 | Steel measuring tap | Deliverd
163580 | 2021-06-25 | Sandstone Lt Grey | Next week delivery
163568 | 2021-06-22 | DG Set | Next week delivery
163561 | 2021-06-19 | Panel board | Co ordinate with supplier
163562 | 2021-06-19 | LT Panels | Co ordinate with supplier
163546 | 2021-06-14 | Air cooled screws chillers | Co ordinate with supplier
163536 | 2021-06-09 | 33KV VCB Switch board | Co ordinate with supplier
163614 | 2021-07-08 | Expensive morter | Double time remove