## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estates
Site: |  | 2021-07-17
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
175281 | 2021-05-11 | Laptop bags | Local purchase
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
175279 | 2021-05-07 | BT Road patching material | Pick up from supplier
175303 | 2021-06-25 | Aerocon pannels | Deliverd
175315 | 2021-07-10 | Panel doors | Deliverd
175318 | 2021-07-14 | Altek lappum | Pick up from ssllp
175319 | 2021-07-14 | Utility tiles | Deliverd