## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-07-17
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
180818 | 2021-07-10 | Kerbee sheets | PO 78661
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
180797 | 2021-06-04 | Bathroom tiles | Deliverd
180799 | 2021-06-09 | Casuraina plants | As per site requirment supplier will deliver
180801 | 2021-06-12 | Flooring tiles | Deliverd
180812 | 2021-06-23 | PPC Cement | Deliverd
180813 | 2021-06-30 | Grills | Pick up from SSLLP
180817 | 2021-07-02 | Wifi cameras | Co ordinate with supplier
180819 | 2021-07-10 | Pannel doors | Deliverd
180820 | 2021-07-17 | Door beeding | Pick up from SSLLP