## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-07-24
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163645 | 2021-07-21 | MCB | PO 78923
163644 | 2021-07-21 | JBL Speakers | Cancelled By MD
163627 | 2021-07-16 | Executive bag | Contact admin for approval
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163647 | 2021-07-21 | SS Screws | Deliverd
163646 | 2021-07-21 | Bluse sheet | Deliverd
163630 | 2021-07-17 | Ring binders | Deliverd
163625 | 2021-07-17 | Coffee powder and Tea Powder | Online purchase
163623 | 2021-07-15 | Umbrella and rain coats | Deliverd
163617 | 2021-07-12 | White papers and blue pens | Deliverd
163598 | 2021-06-29 | Tandoor stone | Deliverd
163585 | 2021-06-26 | Electric bike | August 1 st week delivery
163567 | 2021-06-21 | Z angles | Deliverd
163648 | 2021-07-22 | Panels | Double requisition can be closed
163601 | 2021-06-30 | Cables | Co ordinate with supplier
163600 | 2021-06-30 | Fire safety systems | Co ordinate with supplier
163583 | 2021-06-26 | HT Meter, mounting box | Co ordinate with supplier
163580 | 2021-06-25 | Sand stone | Co ordinate with supplier
163568 | 2021-06-22 | DG Set | Co ordinate with supplier
163561 | 2021-06-19 | Panels | Co ordinate with supplier
163546 | 2021-06-14 | Screw chiller | Co ordinate with supplier