## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-07-24
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
180818 | 2021-07-10 | Kerbee sheets | PO 78661, with md
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
180797 | 2021-06-04 | Bathroom tiles | Deliverd
180801 | 2021-06-12 | Flooring tiles | Deliverd
180813 | 2021-06-30 | Grills | Pick up from SSLLP
180817 | 2021-07-02 | Wifi cameras | Co ordinate with supplier
180819 | 2021-07-10 | Cylendarical lock | Deliverd
180821 | 2021-07-10 | Tan brown granite | Pick up from SOV
180823 | 2021-07-19 | PPC Cement | Supplier will deliver
180826 | 2021-07-26 | 16 amps switches | Deliverd