## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estates
Site: |  | 2021-07-31
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
175281 | 2021-05-11 | Laptop bags | Online purchase follow up with admin
175307 | 2021-07-15 | Laptop chargers | Sent for sys admin approval
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
175279 | 2021-05-07 | BT Road patching material | Pick up from supplier
175318 | 2021-07-14 | Altek lappum | Deliverd
175322 | 2021-07-15 | Al windows | Contact sudarshan for delivery
175323 | 2021-07-19 | MS Square pipe | Deliverd
175325 | 2021-07-20 | Solar power | Contact supplier for delivery