## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-08-07
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing 8mm toughness | Document is Estimation
177492 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177493 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177502 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177503 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177588 | 17.04.2021 | Waterproofing | Document is in estimation
177769 | 30.06.2021 | Grills part 2 | Hold by MD
177770 | 30.06.2021 | Grills part 2 | Hold by MD
177771 | 30.06.2021 | Grills part 2 | Hold by MD
177772 | 30.06.2021 | Grills part 2 | Hold by MD
177802 | 10.07.2021 | Air blower | Material deliverd
177813 | 15.07.2021 | Wipro LED lights | PO 78654
177815 | 15.07.2021 | Wipro LED lights | PO 78615
177860 | 28.07.2021 | Water proofing -Screeding | Po to be issue
177870 | 31.07.2021 | Flat patti | PO 79450
177874 | 02.08.2021 | Gazette plates | PO 79440
177874 | 02.08.2021 | L angle 8mm,MS sq pipe | PO79444
177877 | 03.08.2021 | Ms elbows | PO 79462
177878 | 03.08.2021 | Sprinkler bulb | PO 79465
177884 | 04.08.2021 | Hob & chimney | PO 79511
177885 | 04.08.2021 | Hob & chimney | PO 79512
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177387 | 16.02.2021 | Upvc sliding windows | Work under progress
177472 | 17.03.2021 | Down commers, sprinklers | Work under progress
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478&177479 | 17.03.2021 | Pannel doors part 2 | Half of the material we received remaining supplier arrange the material delivered by next week
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177488 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177498 | 19.03.2021 | Stainless steel sink | Supplier arrange the material delivered by next week
177513 | 20.03.2021 | Spring wire, Tv wire, telephone wire ,Internet cable | Half of the material we received remaining supplier arrange the material material by partially
177559 | 06.04.2021 | Bathroom tiles luna ultra malaysian | Half of the material we received remaining material supplier arrange the material delivered by next week
177562 | 06.04.2021 | Vertrified tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177582 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Half of the material we received remaining material supplier arrange the material delivered by next week
177591 | 20.04.2021 | AMC for Generator Set | Work under progress
177597 | 23.04.2021 | Bath room tiles | Half of the material we received remaining we will pick up from SSLLP next week
177642 | 08.05.2021 | Kitchen unit | Work under progress
177690 | 03.06.2021 | Curb stone | Half of the material received remaining supplier arrange Material delivered by next week
177711 | 07.06.2021 | Thandor stone | Half of the material received remaining supplier arrange Material delivered by next week
177721 | 10.06.2021 | Generator | Suppliers arranging the material Delivered by next week
177762 | 28.06.2021 | Fire doors | Under production
177827 | 19.07.2021 | Ro water plant | Material to be issue
177829 | 21.07.2021 | Carrara tiles | No stock at SSLLP
177844 | 23.07.2021 | Rain water line with MS pipe | Work under progress
177846 | 23.07.2021 | Tan brown Granite | Supplier Arrange the material delivered by next week
177852 | 24.07.2021 | Tan brown Granite | Supplier Arrange the material delivered by next week
177853 | 27.07.2021 | MS Frames Sewage Pump | Supplier Arrange the material delivered by next week
177864 | 29.07.2021 | SS button Screws | Pick up from supplier
177869 | 31.07.2021 | PVC pipes | Deliverd
177879 | 03.08.2021 | Fan rods white color | Deliverd
177880 | 03.08.2021 | Fruit packing covers | Pick up from supplier
177881 | 03.08.2021 | Wall mixtures | Deliverd
177882 | 03.08.2021 | Wall hung Wc | Deliverd
177883 | 04.08.2021 | Blue sheet covers | Deliverd