## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-08-07
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163697 | 2021-08-04 | Membrine | PO 79478
163695 | 2021-08-04 | Street light poles | Cancell this requisition issued a po 79525
163694 | 2021-08-04 | MS Frame and railing | Estimate to be prepaed
163691 | 2021-08-04 | Tandoor stone | PO 79539
163690 | 2021-08-04 | MS Shutter | Requisition sent to mds approval
163682 | 2021-08-02 | Mechanical anchor bolt | PO 79375
163677 | 2021-07-31 | AMC | Quotes to be receive
163676 | 2021-07-31 | Bamboo thadkas | Local purchase by site
163657 | 2021-07-24 | TP Link router | PO 79547
163655 | 2021-07-24 | MS Frames | Cancelled by MD
163702 | 2021-08-04 | Chiller piping | PO 79485
163648 | 2021-07-22 | Panels | Cancell this requisition
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163710 | 2021-08-04 | 3 core copper wire | Deliverd
163693 | 2021-08-04 | DG Set | Delivery as per schdule
163688 | 2021-08-04 | ETP and STP Works | Work under process
163684 | 2021-08-02 | Birla wall care putty | Deliverd
163683 | 2021-08-02 | Barricade | Deliverd
163681 | 2021-08-02 | Anchor bolt, thread rod nuts | Co odinate with supplier for delivery
163679 | 2021-07-31 | Rod cutting blades | Deliverd
163675 | 2021-07-31 | Gova ropes | Deliverd
163674 | 2021-07-30 | Lenovo charger | Co odinate with supplier for delivery
163666 | 2021-07-29 | MS L angle | Co odinate with supplier for delivery
163665 | 2021-07-28 | Bosh level | Deliverd
163663 | 2021-07-27 | Gova ropes | Deliverd
163662 | 2021-07-27 | LT Panels | Co odinate with supplier for delivery
163653 | 2021-07-24 | Colin bottl, handwash | Deliverd
163650 | 2021-07-23 | Plumbing material | Co odinate with supplier for delivery
163625 | 2021-07-15 | Coffee powder | Deliverd
163600 | 2021-06-30 | Fire systems | Co odinate with supplier for delivery
163583 | 2021-06-26 | HT Meter | Co odinate with supplier for delivery
163580 | 2021-06-25 | Sand stone | Co odinate with supplier for delivery
163629 | 2021-07-17 | HT Material | Deliverd
163628 | 2021-07-17 | HT Material | Deliverd