## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-08-07
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
180818 | 2021-07-10 | Kerbee sheets | PO 78661, with md
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
180797 | 2021-06-04 | Bathroom tiles | Deliverd
180813 | 2021-06-30 | Grills | Pick up from SSLLP
180828 | 2021-07-20 | SS Sink | Deliverd
180830 | 2021-07-23 | PVC Reducer tee | Deliverd
180835 | 2021-07-29 | UPVC Sliding windows | Under process