## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-08-14
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163732 | 2021-08-11 | Wipro LED Lights | PO to be issue
163728 | 2021-08-10 | Jerry cans | Pick up from SSLLP
163720 | 2021-08-09 | AMC for Split AC`s | Not recomendable you can do the regular servicing
163718 | 2021-08-09 | MS Frames | PO to be issue
163694 | 2021-08-04 | MS Frame and Railing | Estimate to be prepare
163690 | 2021-08-04 | MS Shutter | Estimate to be prepare
163677 | 2021-07-31 | AMC For Generaor | Local area supplier if you can sugget will give the AMC our
regular supplier is denaying to do the work in thurkapally area
163601 | 2021-06-30 | 33 KV Cable | PO 78457
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163733 | 2021-08-11 | L Folders | Deliverd
163730 | 2021-08-10 | Plumbing material | Deliverd
163729 | 2021-08-10 | Plumbing material | Deliverd
163727 | 2021-08-10 | GI Nipple, teflon tape | Deliverd
163726 | 2021-08-10 | Hakshaw blades | Pick up from SSLLP
163725 | 2021-08-10 | GI Balvalve | Deliverd
163724 | 2021-08-09 | MS Section, MS Plates | Collect from Dilpreet Tubes
163721 | 2021-08-09 | Drill bit | Deliverd
163715 | 2021-08-06 | Plastic chairs | Collect from Siddarth enterprises, pick the cheque at HO-Praveen raju
163705 | 2021-08-07 | MS Box pole | Co ordinate with Surya Electricals
163702 | 2021-08-04 | MS Round pipes | Deliverd
163697 | 2021-08-04 | Membrence | Call supplier for material delivery
163693 | 2021-08-04 | DG Set | Co ordinate with Powerica
163691 | 2021-08-04 | Tandoor stone | Pick up from SOV
163688 | 2021-08-04 | ETC, STP Works | Co ordinate with supplier
163681 | 2021-08-02 | Anchor bolt Thread rods | Deliverd
163674 | 2021-07-30 | Lenovo charger | Pick up from Swetha computers
163666 | 2021-07-29 | MS L angle | Co ordinate with supplier
163664 | 2348-02-04 | MS Railing | Co ordinate with supplier
163662 | 2021-07-27 | LT Pannels | Co ordinate with supplier
163653 | 2021-07-24 | Colin bottles dettol hand wash | Deliverd
163650 | 2021-07-23 | Plumbing material | Co ordinate with supplier
163600 | 2021-06-30 | Fire safety systems | Co ordinate with supplier
163583 | 2021-06-26 | HT Meter | Co ordinate with supplier
163580 | 2021-06-25 | Sand stone tiles | Co ordinate with supplier
163561 | 2021-06-19 | ICOG Panel | Co ordinate with supplier
163735 | 2021-08-13 | High presurre washer | Deliverd