## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Heights
Site: |  | 2021-08-14
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
181611 | 2021-07-07 | Laptop bags | Cancell requisition
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
181640 | 2021-07-10 | Mesurment box | Under process
181614 | 2021-07-10 | Tandoor stone | Deliverd
181645 | 2021-07-30 | Paints | Pick up from SSLLP
181655 | 2021-08-05 | Cement | Direct delivery
181659 | 2021-08-06 | Water bottles | Deliverd
181666 | 2021-08-10 | Cement ventilator | Local purchase