## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Heights
Site: |  | 2021-08-21
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
181611 | 2021-07-07 | Laptop bags | Cancell requisition
181674 | 2021-08-16 | RMC | PO 79849
181675 | 2021-08-17 | ISMB poles | PO 79739
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
181614 | 2021-07-10 | Tandoor stone | Deliverd
181640 | 2021-07-27 | mMesurment box | Delivery by next Monday hopefully
181645 | 2021-07-30 | Paints | Delivery by next Monday hopefully
181666 | 2021-08-10 | Cement ventilator | Local purchase
181669 | 2021-08-12 | Gunny bags | Pick up from SSLLP
181673 | 2021-08-16 | Wooden thadkas | Deliverd