## KNM
Prepared by: | Mounika
Report Date | 28.08.21
Site | Kadakia & Modi Housing
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
21639 | 13.08.21 | BT Patch up material | With in a week delivary
List of requisitions Where PO/WO is prepared and items have not received at site
Nil | Nil | Nil | Nil