## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-08-28
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163732 | 2021-08-11 | Wipro LED Lights | PO 79868
163728 | 2021-08-10 | Jerry cans | PO 80044
163720 | 2021-08-09 | AMC for Split AC`s | Not recomendable you can do the regular servicing
163718 | 2021-08-09 | MS Frames | PO to be issue
163694 | 2021-08-04 | MS Frame and Railing | Estimate to be prepare
163690 | 2021-08-04 | MS Shutter | Estimate to be prepare
163677 | 2021-07-31 | AMC For Generaor | Local area supplier if you can sugget will give the AMC our
regular supplier is denaying to do the work in thurkapally area
163601 | 2021-06-30 | 33 KV Cable | PO 78457
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163724 | 2021-08-09 | MS Section, MS Plates | Collect from Dilpreet Tubes
163715 | 2021-08-06 | Plastic chairs | Collect from Siddarth Enterprises
163705 | 2021-08-07 | MS Box pole, side arm, nut bolts, MCCB | Co ordinate with supplier
163702 | 2021-08-04 | MS Round pipes | Deliverd
163697 | 2021-08-04 | Membrence | Deliverd
163693 | 2021-08-04 | DG Set | Co ordinate with supplier
163691 | 2021-08-04 | Tandoor stone | Collect from SSLLP
163688 | 2021-08-04 | ETP, STP | Work under process
163674 | 2021-07-30 | Lenovo charger | Pick up from supplier
163666 | 2021-07-29 | MS L angle | Pick up from supplier
163664 | 2021-07-28 | MS Railing | Pick up from supplier
163622 | 2021-07-27 | LT Panels | Co ordinate with supplier
163600 | 2021-06-30 | Fire safery system | Work under process
163583 | 2021-06-26 | HT Meters | Work under process
163561 | 2021-06-19 | ICOG Panel | Work under process
163735 | 2021-08-13 | Haigh pressure washer | Pick up from supplier
163715 | 2021-08-06 | Plastic chairs | Double time, delete it
163705 | 2021-08-07 | MS Box pole, side arm, nut bolts, MCCB | Double time, delete it