## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-09-04
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
180844 | 2021-08-12 | Grills | PO 79743
180848 | 2021-08-18 | RCC Covers | Deliverd
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
180797 | 2021-06-04 | Bathroom tiles | close the po and req for the received qty and send a fresh request for balance requirment
180813 | 2021-06-30 | Grills | Deliverd
180818 | 2021-07-10 | Kerbee sheets, MS Square pipe, MS Flat patti | Deliverd
180835 | 2021-07-29 | UPVC Track sliding windows | Co ordinate with supplier
180839 | 2021-08-08 | Panel door | Deliverd
180842 | 2021-08-12 | PVC Connection | Deliverd
180847 | 2021-08-17 | WIFI Security camera | Next week delivery
180850 | 2021-08-18 | Plumbing material | Deliverd