## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-09-11
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177492 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177493 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177502 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177503 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177588 | 17.04.2021 | Waterproofing | Rates to be Finalized
177769 | 30.06.2021 | Grills part 2 | Hold by MD
177770 | 30.06.2021 | Grills part 2 | Hold by MD
177771 | 30.06.2021 | Grills part 2 | Hold by MD
177772 | 30.06.2021 | Grills part 2 | Hold by MD
177815 | 15.07.2021 | Wipro LED lights | Cancelled by MD
177860 | 28.07.2021 | Water proofing -Screeding | Po to be issue
177906 | 10.08.2021 | SS railing | Po to be issue
177913 | 14.08.2021 | Water Proofing Screeding | Rates To be finalized
177916 | 14.08.2021 | Cutter Type Dewatering pump | Cancelled by MD
177923 | 16.08.2021 | Armoured cable | PO 79765
177924 | 16.08.2021 | Hydrant Valve | PO 79791
177925 | 16.08.2021 | Booster Pump Kirloskar | PO 79791
177926 | 17.08.2021 | Ceasal pinia Plats | PO 79773
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177152 | 26.11.2020 | Passenger lift& Sevice lift | Work under Progress
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177387 | 16.02.2021 | Upvc sliding windows | Work under progress
177472 | 17.03.2021 | Down commers, sprinklers | Work under progress
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478&177479 | 17.03.2021 | Pannel doors part 2 | Half of the material we received remaining supplier arrange the material delivered by next week
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177488 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177491 | 18.03.2022 | Grills part 1 | Partially delivered
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177498 | 19.03.2021 | Stainless steel sink | Half of the material we received remaining material supplier arrange the material delivered by next week
177513 | 20.03.2021 | Spring wire, Tv wire, telephone wire ,Internet cable | Half of the material we received remaining supplier arrange the material material by partially
177559 | 06.04.2021 | Bathroom tiles luna ultra malaysian | Half of the material we received remaining material supplier arrange the material delivered by next week
177562 | 06.04.2021 | Vertrified tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177582 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Half of the material we received remaining material supplier arrange the material delivered by next week
177711 | 07.06.2021 | Tandor Stone | Partially Delivered
177721 | 10.06.2021 | Generator | Suppliers arranging the material Delivered by next week
177762 | 28.06.2021 | Fire doors | Under production
177827 | 23.07.2021 | RO plant | Work under Progress
177829 | 21.07.2021 | Carrara Tiles | No stock At Supplier
177844 | 23.07.2021 | Rain water line MS pipe | Supplier Arrange the material delivered by next week
177853 | 27.07.2021 | Cutter type sewage Pump | Pick up from SSLLP
177869 | 31.07.2021 | PVC Pipes | Deliverd
177884 | 04.08.2021 | Chimney ,hob | Deliverd
177896 | 07.08.2021 | Vertrified tiles grey light,Regal beige | Pick up from SSLLP
177901 | 07.08.2021 | Vetrified tiles Regal beige | Deliverd
177903 | 10.08.2021 | Insulation tapes | Deliverd
177904 | 10.08.2021 | SS Special Screws | Deliverd
177907 | 10.08.2021 | Arldite,jantapaste,Grout | Deliverd
177914 | 14.08.2021 | Submersible Pump with3 phase Stater | Deliverd
177915 | 14.08.2021 | Cp Sq jalli without Hole | Deliverd
177917 | 14.08.2021 | 3 Core Plat Cable | Pick up from supplier
177921 | 16.08.2021 | Bleaching powder | Deliverd