## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estaes
Site: |  | 2021-09-18
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where where PO/WO not prepared 3 working days after requisition
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
175279 | 2021-05-07 | BT Road patching material | Co ordinate with supplier
175307 | 2021-06-28 | Laptop chargers | Pick up from supplier
175325 | 2021-07-20 | Solar power | Co ordinate with supplier
175349 | 2021-08-04 | LED Lights | Deliverd
175350 | 2021-08-10 | Electrical wires | Deliverd
175345 | 2021-08-04 | Ball cocks | Deliverd