## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-09-25
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177492 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177493 | 18.03.2021 | Wall mixture | Rates to be finalized by MD
177502 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177503 | 19.03.2021 | Sanitary wall hung WC | Rates to be finalized by MD
177769 | 30.06.2021 | Grills part 2 | Cancelled, send new requisition
177770 | 30.06.2021 | Grills part 2 | Cancelled, send new requisition
177771 | 30.06.2021 | Grills part 2 | Cancelled, send new requisition
177772 | 30.06.2021 | Grills part 2 | Cancelled, send new requisition
177937 | 20.08.2021 | Swimming pool Equipments Supply | Rates with MD for finalization
177989 | 08.09.2021 | Splits A/c, Cassette A/c | Po to be issue
177995 | 15.09.2021 | Camera | Online purchase
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177152 | 26.11.2020 | Passenger lift& Sevice lift | Work under Progress
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177387 | 16.02.2021 | Upvc sliding windows | Work under progress
177472 | 17.03.2021 | Down commers, sprinklers | Work under progress
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478&177479 | 17.03.2021 | Pannel doors part 2 | Half of the material we received remaining supplier arrange the material delivered by next week
177480 | 18.03.2021 | Upvc 2.5 track French window part 1 | Work under progress
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177488 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177491 | 18.03.2022 | Grills part 1 | Partially delivered
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177498 | 19.03.2021 | Stainless steel sink | Partially delivered
177513 | 20.03.2021 | Spring wire, Tv wire, telephone wire ,Internet cable | Half of the material we received remaining supplier arrange the material material by partially
177559 | 06.04.2021 | Bathroom tiles luna ultra malaysian | Half of the material we received remaining material supplier arrange the material delivered by next week
177562 | 06.04.2021 | Vertrified tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177582 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Partially delivered
177721 | 10.06.2021 | Generator | Deliverd
177762 | 28.06.2021 | Fire doors | Work Under Progress
177813 | 15.07.2021 | LED Wipro Lights | Partially delivered
177827 | 23.07.2021 | RO plant | Work under Progress
177829 | 21.07.2021 | Carrara tiles | Pick up from GMR
177844 | 23.07.2021 | Rain water line MS pipe | Material not available at Supplier
177853 | 27.07.2021 | MS frame for cutter type | Under fabrication
177860 | 28.07.2021 | Water proofing Screeding | Work under progress
177896 | 07.08.2021 | Vertrified tiles grey light,Regal beige | Half of the Material is ready we will pick up from GMR
177901 | 07.08.2021 | Vetrified tiles Regal beige | Half of material we received remaining we will pick up from GMR
177913 | 14.08.2021 | Water proofing -screeding | Work under progress
177970 | 03.09.2021 | Square pipe 1.5mm | Partially delivered
177973 | 04.09.2021 | MS pipe B class 20’lenght | Partially delivered
177991 | 13.09.2021 | Tan brown granite | Material is ready we will pick up on Monday
177999 | 15.09.2021 | Sadar ali Grey Granite | Supplier Arrange the Material Delivered by Next week
178001 | 16.09.2021 | Tandoor Rough Stones | Supplier Arrange the Material Delivered by Next week
178005 | 18.09.2021 | Panel Boards 12.5 HP | Supplier Arrange the Material Delivered by Next week
178006 | 18.09.2021 | Tan brown Granite | Material is ready we will pick up on Monday
178007 | 18.09.2021 | MCB 40Amps | Material is ready we will pick up on Monday
178008 | 18.09.2021 | MS round pipe | Supplier Arrange the Material Delivered by Next week
178010 | 21.09.2021 | Wipro Flood light | Material is ready we will pick up on Monda