## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-09-25
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163718 | 2021-08-09 | MS Frames | Under rates negotiation
163677 | 2021-07-31 | AMC For Generaor | Local area supplier if you can sugget will give the AMC our
regular supplier is denaying to do the work in thurkapally area, you can do it locally
163784 | 2021-08-31 | Shutters | Cancelled
163694 | 2021-08-04 | MS Gate | Material deliverd po to be issue
163746 | 2021-08-18 | Laptop | Co ordinate with System admin
163770 | 2021-08-28 | Anchor for structural glazing | WO, Material deliverd
163774 | 2021-08-30 | Safety material | PO to be issue
163798 | 2021-09-03 | Chillers | PO to be issue
163830 | 2021-09-09 | Rest room partations | PO to be issue
163834 | 2021-09-09 | MS Shutters | Rates negotiation
163844 | 2021-09-15 | Laptop bag adapter | Online purchase
163855 | 2021-09-17 | PVC Material | PO 81044
163856 | 2021-09-17 | MCCB | Clarification requires from Balmurali
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163510 | 2021-06-03 | Tiles | Partly delivered
163561 | 2021-06-19 | 33KV Indoor panel | Co ordinate with supplier
163580 | 2021-06-25 | Nitco tiles | Partly delivered
163383 | 2021-06-26 | HT Metering cubical and panel | Co ordinate with supplier
163662 | 2021-07-27 | LT Panels | Co ordinate with supplier
163688 | 2021-08-04 | ETP and STP | Work under process
163693 | 2021-08-04 | DG Set | Delivery in october
163732 | 2021-08-11 | Wipro street light | Co ordinate with supplier
163740 | 2021-08-16 | Groundfos make pump | Co ordinate with supplier
163786 | 2021-09-01 | Nut bolts | Supplier will arrenge the material
163797 | 2021-09-03 | UPS | Delivery in october
163802 | 2021-09-03 | Electrical conductiing material | Pick up from SSLLP
163806 | 2021-09-04 | Tissue paper | LP By raghu co ordinate with him
163808 | 2021-09-04 | Flat pipes | Admin to follow up
163819 | 2021-09-08 | PVC Material | Deliverd
163824 | 2021-09-09 | PVC Tent and canvas tent | Supplier will arrenge the material
163829 | 2021-09-09 | Chiller piping material | Material ready to deliver from supplier
163836 | 2021-09-11 | Isolater | Deliverd
163837 | 2021-09-11 | Ring binder files | Follwup with admin
163841 | 2021-09-13 | CR White paints | Deliverd
163848 | 2021-09-16 | Birla white care putty | Pick up from supplier
163850 | 2021-09-16 | Helmets | Pick up from supplier
163851 | 2021-09-17 | Agromesh | Pick up from supplier
163859 | 2021-09-18 | Vishaka cement board | Deliverd