## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-09-25
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
180835 | 2021-07-29 | UPVC Track sliding windows | Deliverd
180844 | 2021-08-12 | Grills | Under fabrication
180847 | 2021-08-17 | WIFI Security camera | Next week delivery
180851 | 2021-08-23 | Wash basin | Deliverd
180856 | 2021-09-15 | GI Ball valve | Pick up from Praful sanitary
180867 | 2021-09-15 | CPVC Material | Pick up from SSLLP
180868 | 2021-09-15 | PVC Door tee | Pick up from SSLLP
180871 | 2021-09-18 | Pannel doors | Deliverd