## KNM
Prepared by: | Kavitha
Report Date | 30-09-2021
Site | GV Discovery center pvt.ltd
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
13261 | 25-6-2021 | Printer | Order placed
13326 | 17-7-2021 | Broucher Stand | Cancelled (Send a new requisition)
13335 | 28-08-2021 | Sprit level tapes | Pick up from SSLLP
13325 | 13-08-2021 | TP link router with SIM card | will be deliverd on 4th Oct
13337 | 1-1-2021 | Shoes for ladies | Pick up from SSLLP
13351 | 20-09-2021 | CPVC Material | PO to be issue
13345 | 2021-03-09 | RO Plant | Follow up with suppleir
List of requisitions Where PO/WO is prepared and items have not received at site
13339 | 2021-01-09 | Steel tapes | Follow up with suppleir
13353 | 16-09-2021 | Varmi compost | Follow up with suppleir
13356 | 20-09-2021 | RMC | Follow up with suppleir