## KNM
Prepared by: | Kavitha
Report Date | 23-09-2021
Site | Aedis Developers LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
100487 | 15-09-2021 | RCC square Cvers | Follow up with suppleir
List of requisitions Where PO/WO is prepared and items have not received at site
100488 | 15-09-2021 | Curb Stone | Follow up with suppleir
100485 | 14-09-2021 | Panel doors | Prtly deliverd, balance to be pick from SSLLP
100484 | 14-09-2021 | MS window | pick up from ssllp
100478 | 2021-07-09 | Isolator, moduler pltes | Prtly deliverd, balance to be pick from SSLLP
100473 | 2021-06-09 | Steel sink | Prtly deliverd, balance to be pick from SSLLP
100471 | 2021-02-09 | Electrical wires | pick up from ssllp
100467 | 2021-02-09 | Bathroom tiles | pick up from ssllp
100457 | 27-08-2021 | False ceiling | Follow up with suppleir
100449 | 17-08-2021 | Doors and hardware | Follow up with suppleir
100437 | 2021-06-08 | Panel doors | Prtly deliverd, balance to be pick from SSLLP
100436 | 2021-02-08 | Electrical wires | Prtly deliverd, balance to be pick from SSLLP
100430 | 28-7-2021 | RO Plant | Follow up with suppleir
100429 | 26-07-2021 | PVC coupling | Prtly deliverd, balance to be pick from SSLLP
100403 | 2021-03-07 | Bathroom tiles | Prtly deliverd, balance to be pick from MPL | MPL