## KNM
Prepared by: | Kavitha
Report Date | 21-10-2021
Site | Aedis Developers LLP
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
100531 | 13-10-2021 | 1.75HP Pump | pick up from supplier
100530 | 2021-12-10 | cement jali | pick up from ssllp
100528 | 2021-11-10 | 2HP Pumps starter | pick up from supplier
100526 | 2021-09-10 | water proofing | pick up from supplier
100506 | 2021-04-10 | Diesel barrel cans | pick up from supplier
List of requisitions Where PO/WO is prepared and items have not received at site
100529 | 2021-12-10 | White cement | pick up from ssllp
100524 | 2021-09-10 | PVC bends | follow up with supplier
100523 | 2021-10-10 | Al services wires | partly delivered from ssllp
100522 | 2021-08-10 | Hanging lights | follow up with supplier
100521 | 2021-08-10 | LED Ceiling lights | follow up with supplier
100515 | 2021-07-10 | Door beedings | pick up from ssllp
100514 | 2021-06-10 | SS Name plates | pick up from supplier
100513 | 2021-06-10 | SS Name plate vowel shape | pick up from supplier
100509 | 2021-05-10 | MS pipe | partly delivered from ssllp
100508 | 2021-05-10 | MS Round pipe | partly delivered from ssllp
100505 | 29-10-2021 | Solid bricks | partly delivered from ssllp
100500 | 22-09-2021 | Armoured cables | pick up from supplier
100490 | 18-09-2021 | MI Cameras | pick up from supplier
100484 | 14-09-2021 | MS windows | pick up from ssllp
100430 | 28-07-2021 | RO plants | pick up from supplier