## Site reply
Prepared by: |  | Prabhakar
Date: |  | GVRC
Site: |  | 2021-10-23
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
163844 | 2021-09-15 | Laptop bag | Online purchase
163856 | 2021-09-17 | MCCB | PO 82188
163872 | 2010-09-18 | Traffic cone with chain | PO to be issue
163884 | 2021-09-22 | Barri gate stickers | Promotions to follow up, as per Prasad he sent already kindly close this req
163910 | 2021-09-25 | Electric motor starter | PO 82146
163913 | 2021-09-27 | Lugs chrimping machine | Local purchase by tomorrow
163961 | 2021-01-04 | Plywood sheets | PO 82128
163938 | 2021-10-06 | Cannon camera | Online purchase
164011 | 2021-10-18 | Busduct material | PO issued in word format not in Purchase database, close the req, follow up with waseem for PO and material delivery
164012 | 2021-10-14 | MS Falt patti | Local purchase by site u can cloe this requisition
164032 | 2021-10-19 | Landline phone | Online purchase
164055 | 2021-10-23 | Bentonite bag | PO 82009
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
163510 | 2021-06-03 | Tiles | an email has been sent to hestia regarding the balance tiles awaiting reply
163662 | 2021-07-27 | LT Panels | Co ordinate with supplier
163688 | 2021-08-04 | ETP and STP | Work under process
163693 | 2021-08-04 | DG Set | Delivery under process
163797 | 2021-09-03 | UPS | Delivery under process
163834 | 2021-09-09 | Shutters | Work under process
163889 | 2021-09-23 | Safety equipments | Deliverd
163898 | 2021-09-24 | Plates, 250x250x10mm | Deliverd
163918 | 2021-09-27 | Puf saddles | Work under process
163945 | 2021-10-01 | MS Stand | Pick up from SSLLP
163976 | 2021-10-06 | Solid bricks | Follow up with supplier he will deliver as per site requirment
163984 | 2021-10-06 | PVC False ceiling | Work under process
163988 | 2021-10-09 | Al wires | Work under process
164003 | 2021-10-11 | Stained décor cold tiles | Co ordinate with supplier
164001 | 2021-10-11 | CLC Blocks | co ordinate with supplier, shanmukha
164016 | 2021-10-18 | MS Stand | Pick up from SSLLP
164028 | 2021-10-19 | Safety shoes | Pick up from SSLLP
164042 | 2021-10-20 | Line dori | deliverd
164044 | 2021-10-21 | Mortise locka and Hardware | deliverd
164049 | 2021-10-20 | Mortise locka and Hinges | deliverd
164051 | 2021-10-22 | Roff stone tile, adhesive, lappum patti | Co ordinate with supplier
164052 | 2021-10-22 | Anchor set chemical | Pick up from SSLLP