## Site reply
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Heights
Site: |  | 2021-10-23
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
181725 | 2021-10-05 | MS Compound wall grills | Material under fabrication after that PO will be made as per the exact weight
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
181703 | 2021-09-18 | Al windows | Deliverd
181735 | 2021-10-13 | Curing pipe | Deliverd
181736 | 2021-10-13 | Hand pully trolly | Next week delivery