## Sheet1
Prepared by: | Prabhakar
Date: | Modi Properties Pvt Ltd-May flower platinum
Site: | 2021-10-16
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisitions where PO/WO not prepard 3 working days after requisition
177134 | 18.11.2020 | SS Railing8mm | Estimation with Md for Approval
177492 | 18.03.2021 | Wall mixture | Cancel this requisition and raise the new one
177493 | 18.03.2021 | Wall mixture | Cancel this requisition and raise the new one
177502 | 19.03.2021 | Sanitary wall hung WC | Cancel this requisition and raise the new one
177503 | 19.03.2021 | Sanitary wall hung WC | Cancel this requisition and raise the new one
177937 | 20.08.2021 | Swimming pool Equipments Supply | PO issued in word format, you may close the requisition
177995 | 15.09.2021 | Camera | Online purchase
178046 | 01.10.2021 | Ponding Sheet | Online purchase
178050 | 04.10.2021 | AMF panel | Document is estimate
178069 | 07.10.2021 | Grease | Deliverd to site by local purchase, close this req
178088 | 11.10.2021 | ISS Flange | Po to be issue
178108 | 19.10.2021 | Birla Putty,White Cement | PO 82041
List of requisitions where PO/WO is prepared and items have not been received at site beyond the lead time:
177152 | 26.11.2020 | Passenger lift& Sevice lift | Work under Progress
177386 | 16.02.2021 | Upvc sliding windows | Work under progress
177472 | 17.03.2021 | Down commers, sprinklers | Work under progress
177476 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177477 | 17.03.2021 | SS railing with 8mm toughned glass | Work under progress
177478&177479 | 17.03.2021 | Pannel doors part 2 | Half of the material we received remaining supplier arrange the material delivered by next week
177481 | 18.03.2021 | Upvc 2.5 track French window part 2 | Work under progress
177487 | 18.03.2021 | MCBs,modular plate ,socket | Partially delivered
177488 | 18.03.2021 | MCBs,modular plate ,socket | Half of the material we received remaining material supplier arrange the material delivered by next week
177490 | 18.03.2021 | Sliding window UPVC | Work under progress
177496 | 19.03.2021 | UPVC sliding windows | Work under progress
177498 | 19.03.2021 | Stainless steel sink | Supplier Arrange the Material Delivered by Next week
177513 | 20.03.2021 | Spring wire, Tv wire, telephone wire ,Internet cable | Half of the material we received remaining supplier arrange the material material by partially
177559 | 06.04.2021 | Bathroom tiles luna ultra malaysian | Half of the material we received remaining material supplier arrange the material delivered by next week
177562 | 06.04.2021 | Vertrified tiles | Half of the material we received remaining material supplier arrange the material delivered by next week
177582 | 17.04.2021 | Grigio serena,stained concrete beige& concrete grigio | Partially delivered
177711 | 07.06.2021 | Thandor stone | Half of the material we received remaining material supplier arrange the material delivered by next week
177813 | 15.07.2021 | LED Wipro Lights | Partially delivered
177844 | 23.07.2021 | Rain water line MS pipe | Under fabrication
177853 | 27.07.2021 | MS frame for cutter type | Supplier Arrange the Material Delivered by Next week
177896 | 07.08.2021 | Vertrified tiles ,beige,Grigio,urban wood | Half of the Material is ready we will pick up from GMR
177901 | 07.08.2021 | Vetrified tiles urban wood natural, | Half of material we received remaining we will pick up from GMR
178013 | 21.09.2021 | Tiles urbanwood natural,Crema Marfil | Half of material we received remaining we will pick up from GMR
178017 | 22.09.2021 | L angle, Wooden Screws | Deliverd.
178040 | 01.10.2021 | Sadar ali Grey Granite | Deliverd
178051 | 04.10.2021 | Dado country rosso ,Country black berry | Pick up from SSLLP
178058 | 05.10.2021 | Tan Brown Granite | Pick up from SSLLP
178070 | 07.10.2021 | Fire safety Door | Deliverd
178074 | 07.10.2021 | Fire extinguishers | Deliverd
178082 | 08.10.2021 | LED Flood light | To be exchanged, supplier don’t have the stock at present
178090 | 12.10.2021 | Janata paste ,grout | Deliverd
178091 | 12.10.2021 | Starters | Material is Ready we will pick up on Monday
178092 | 12.10.2021 | Sadar Ali Grey | Pick up from SSLLP
178093 | 12.10.2021 | Sadarali White,Grey | Supplier Arrange the Material Delivered by Next week
178105 | 18.10.2021 | Round Cp Jali Flip type | Pick up from Praful sanitary
178110 | 19.10.2021 | Sadarali Grey | Pick up from SSLLP