## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Vista Homes
Site: |  | 2021-10-02
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where items have not been received st site beyond the lead time.
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
180835 | 2021-07-29 | UPVC Track sliding window | Deliverd
180847 | 2021-08-17 | Wifi security cameras | This week delivery
180865 | 2021-09-15 | GI ball valve | co ordinate with supplier
180867 | 2021-09-15 | CPVC brass mta,cpvc brass elbow | deliverd
180869 | 2021-09-15 | UPVC Track sliding window | co ordinate with supplier
180875 | 2021-09-27 | Scerws and fishers | Deliverd
180876 | 2021-10-01 | MS Pipes | Deliverd
180878 | 2021-10-04 | MS L angle patti MS flat patti | Deliverd
180880 | 2021-10-12 | 25 Amps change over switch | Deliverd