## Sheet1
Prepared by: |  | Prabhakar
Date: |  | Nilgiri Estaes
Site: |  | 2021-10-09
Requisition No | Requisition Date | Material Descscription | Purchase Manager - Remarks | Material delivered? | If material is not delivered - is delay justified?
List of requisition where where PO/WO not prepared 3 working days after requisition
List of Requisitions where PO/WO is prepard and items have not been received at site beyond the lead time
175325 | 2021-07-20 | Solar power | This week supplier will finish the work
175394 | 2021-10-08 | Earth pits | Deliverd
175402 | 2021-10-14 | Flat patti, square rod, suqare pipe | Deliverd