## KNM
Prepared by: | Kavitha
Report Date | 30-10-2021
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
94928 | 20-10-201 | Door beeding nails | PO No- 82157
94927 | 20-10-2021 | Screws, L patti | PO No- 82160
94924 | 20-10-2021 | MS balcony | PO No- 82107
94923 | 20-10-2021 | AL windows | Esimation with MD for approval
94922 | 20-10-2021 | Door beeding | PO No- 82125
94921 | 20-10-2021 | Doors and hardware | PO No- 82118
94920 | 20-10-2021 | Doors and hardware | PO No- 82091
94919 | 20-10-2021 | AL windows | PO No-82102
94918 | 20-10-2021 | pop Screws | PO No- 82158
94916 | 20-10-2021 | False ceiling | PO No- 82090
94915 | 20-10-2021 | Switches | PO No- 81991
94914 | 20-10-2021 | Electrical wires | PO No- 81989
94905 | 2021-12-10 | Gum tapes | PO No- 82124
List of requisitions Where PO/WO is prepared and items have not received at site
94926 | 20-10-2021 | Altek lappum bags | pick up from SSLLP
94925 | 20-10-2021 | CP Square jali | pick up from SSLLP
94917 | 20-10-2021 | Altek luppum bags | pick up from SSLLP
94910 | 14-10-2021 | Electrical cunductors | pick up from SSLLP
94909 | 2021-12-10 | GI Clamps, brackets | Follow up with suppleir
94908 | 14-10-2021 | plain elbow | pick up from SSLLP
94907 | 2021-12-10 | PVC pipes, palin tee | Partly delivered
94906 | 2021-12-10 | Blue sheets | pick up from SSLLP
94904 | 2021-10-11 | Flats files | pick up from SSLLP
94903 | 2021-11-10 | wiper | Partly delivered
94902 | 2021-10-09 | Templates | Follow up with suppleir
94901 | 2021-10-09 | MS L angle | Follow up with suppleir
94888 | 21-09-2021 | MS stools | pick up from SSLLP
94874 | 26-08-202 | 3 mm MS L angle | Follow up with suppleir