## KNM
Prepared by: | Kavitha
Report Date | 2021-11-04
Site | BRGV
List of requisitions Where PO/WO not prepared 3 working days after requisition:
Requisition No | Requisition Date | Material Descscription | Purchase Officer - Remarks | Material delivered? | If material is not delivered - is delay justified?
94923 | 20-10-2021 | AL windows | Estimate to be prepared
List of requisitions Where PO/WO is prepared and items have not received at site
94936 | 27-10-2021 | Single socket pvc pipe | pick up from SSLLP
94935 | 26-10-2021 | Binder clips | pick up from SSLLP
94928 | 22-10-2021 | Door beeding nails | Follow up with suppleir
94926 | 20-10-2021 | Altek lappam | pick up from SSLLP
94924 | 20-10-2021 | MS railing | Follow up with suppleir
94922 | 20-10-2021 | door beeding | pick up from SSLLP
94921 | 20-10-2021 | Door and hardware | Partly delivered
94919 | 20-10-2021 | Al windows | Partly delivered
94918 | 20-10-2021 | POP Screws | pick up from SSLLP
94917 | 20-10-2021 | Altek lappum | Partly delivered
94920 | 20-10-2021 | Doors and hardware | Follow up with suppleir
94916 | 20-10-2021 | False ceiling | Follow up with suppleir
94914 | 20-10-2021 | Electrical wires | pick up from SSLLP
94909 | 2021-10-12 | GI Clamps,brackets | Follow up with suppleir
94907 | 2021-10-12 | PVC pipes | Partly delivered
94905 | 2021-10-12 | Gum tapes | Follow up with suppleir
94909 | 2021-10-11 | flat files | pick up from SSLLP
94902 | 2021-10-09 | templates | pick up from SSLLP
94901 | 2021-10-09 | MS L Angle | Follow up with suppleir
94888 | 21-09-2021 | MS stool | pick up from SSLLP
94874 | 26-08-2021 | 3mm MS l angle | Follow up with suppleir